## Description
The Flaw of Averages in Project Completion: Why Everything is Behind Schedule
Experiment with the Release Target
on the Model Sheet
Copyright © 2013 ProbabilityManagement.org, all rights reserved.
www.probabilitymanagement.org
Release Date given the Average Task Durations is 6 weeks
Actual Average Release Date is 7.8 weeks
Scroll through duration scenarios here
The Release Date formula (D19) drives the Data Table on the PMTable sheet while running duration scenarios through cells D8 through D17.
Adjust Release Target and see your chances of meeting it
Distribution of Actual Time to Release
Uncertain Durations
Uncertain Durations
Uncertain Durations
The Average Project Completion Time is greater than that predicted by the Average Durations of the underlying tasks, because the project is not done until the last task is done

## Model
[11 empty] | 0 | 1001
Schedule
| Average | Completing a Software Project
|  | weeks to release |  |  |  | 6
Task | Time to Complete | [6 empty] | Average | Target | Chance
Description | in weeks | [5 empty] | Released | 7.8405 | 7 | 9.5%
Subroutine 1 | 6 |  | 0 | 6 | 0
Subroutine 2 | 6 |  | 0 | 0
Subroutine 3 | 6 |  | 6 | 0 | 0
Subroutine 4 | 6 |  | 6 | 0 | 0
Subroutine 5 | 6 |  | 6 | 0 | 0
Subroutine 6 | 6 |  | 6 | 0 | 0
Subroutine 7 | 6 |  | 6 | 0 | 0
Subroutine 8 | 6 |  | 6 | 0 | 0
Subroutine 9 | 6 |  | 6 | 0 | 0
Subroutine 10 | 6 |  | 6 | 0 | 0
|  |  | 6 | 0 | 0
Released | 6 |  | 6 | 0 | 0
Copyright © 2013 ProbabilityManagement.org, all rights reserved.
www.probabilitymanagement.org
Note on Q7: Chance of finishng in targeted number of weeks or less
Note on Q26: Chance of penalty of targeted amount or less

## Library
Subroutines - Duration in Weeks
Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | Sub 8 | Sub 9 | Sub 10
7.56 | 5 | 5.11 | 7.38 | 7.26 | 3.76 | 6.41 | 4.4 | 5.19 | 7.68 | 1000 | Number of trials
4.95 | 5.81 | 5.94 | 7.82 | 5.06 | 4.62 | 5.43 | 6.07 | 4.62 | 6.45
6.12 | 4.04 | 7.05 | 5.63 | 5.23 | 5.4 | 4.39 | 5.89 | 6.24 | 5.98 | Table position of Average
7.03 | 7.61 | 5.55 | 7.13 | 5.17 | 4.26 | 7.77 | 4.36 | 6.61 | 6.5 | 1001
7.53 | 5.75 | 3.8 | 6.01 | 6.86 | 6.98 | 6.36 | 4.39 | 7.49 | 6.36
6.64 | 7.96 | 6.08 | 4.83 | 7.45 | 5.66 | 4.77 | 7.84 | 5.28 | 5.52
4.28 | 4.83 | 5.45 | 5.68 | 3.72 | 6.23 | 3.61 | 7.26 | 4.5 | 6.48
3.97 | 4.17 | 7.83 | 6.42 | 4.99 | 6.88 | 6.8 | 7.6 | 3.84 | 6.09
6.36 | 6.54 | 5.13 | 5.33 | 4.81 | 5.62 | 3.09 | 7.2 | 5.47 | 4.74
6.7 | 3.37 | 6.51 | 5 | 4.32 | 4.86 | 6.03 | 6.41 | 6.15 | 4.15
7.79 | 7.7 | 5.81 | 5.6 | 4.74 | 4.81 | 6.34 | 5.68 | 6.51 | 4.44
7.22 | 5.28 | 6.23 | 7.57 | 5.65 | 6.77 | 6.98 | 4.76 | 6.27 | 7.47
6.27 | 4.26 | 4.82 | 6.1 | 5.19 | 8.01 | 6.9 | 5.41 | 7.13 | 8.22
5 | 5.01 | 5.54 | 5.43 | 3.47 | 6.71 | 6.38 | 6.42 | 5.61 | 5.87
5.87 | 6.04 | 6.44 | 7.4 | 5.94 | 5.81 | 4.89 | 8.79 | 7.56 | 5.17
6.08 | 7.3 | 7.36 | 4.98 | 7.63 | 5.19 | 5.45 | 6.71 | 6.77 | 4.34
6.35 | 5.25 | 7.84 | 6.94 | 5.27 | 5.95 | 6.22 | 4.46 | 6.42 | 6.39
5.77 | 6.18 | 6.12 | 5.74 | 6.65 | 6.58 | 8.2 | 5.8 | 4.77 | 5.6
6.49 | 8.28 | 5.84 | 4.5 | 3.34 | 3.89 | 4.97 | 8.31 | 5.05 | 7.87
5.45 | 6.01 | 4.65 | 4.08 | 5.54 | 5.18 | 7.66 | 6.67 | 3.37 | 4.38
7.39 | 8.24 | 5.71 | 6.71 | 5.81 | 5.92 | 8.36 | 5.75 | 5.38 | 8.14
5.32 | 6.59 | 7.09 | 4.6 | 6.56 | 5.83 | 7.6 | 5.76 | 4.48 | 4.58
3.21 | 5.97 | 6.27 | 6.92 | 5.76 | 5.83 | 8 | 7.48 | 4.93 | 5.46
5.61 | 5.64 | 4.89 | 5.9 | 4.84 | 7.23 | 4.96 | 7.17 | 6.75 | 7.95
6.01 | 5.58 | 5.7 | 7.59 | 4.67 | 5.46 | 6.89 | 3.83 | 4.15 | 6.51
7.57 | 7.1 | 4.99 | 4.03 | 4.85 | 5.85 | 5.66 | 7.34 | 6.15 | 7.35
3.89 | 6.67 | 4.6 | 6.55 | 6.67 | 5.39 | 4.69 | 8.08 | 6.63 | 6.14
4.98 | 5.88 | 6.56 | 5.86 | 4.25 | 5.43 | 5.64 | 6.16 | 5.44 | 6.77
4.63 | 5.44 | 4.67 | 5.22 | 3.39 | 6.09 | 5.97 | 6.01 | 5.01 | 5.98
6.18 | 7.77 | 8.22 | 5.79 | 5.27 | 4.91 | 7.04 | 3.81 | 6.73 | 5.5
6.71 | 5.05 | 5.59 | 6.16 | 7.43 | 5.17 | 5.31 | 6.57 | 7.99 | 5.32
6.77 | 5.85 | 7.74 | 5.23 | 3.89 | 4.98 | 6.59 | 7.24 | 3.41 | 7.39
7.58 | 5.47 | 5.76 | 8.09 | 6.75 | 7.7 | 6.4 | 6.77 | 8.55 | 6.27
7.5 | 5.4 | 4.42 | 7.75 | 5.93 | 6.2 | 5.87 | 5.93 | 6.08 | 5.82
4.62 | 8.1 | 6.26 | 4.22 | 3.51 | 5.08 | 6.25 | 7.54 | 4.89 | 6.86
5.84 | 6.61 | 6.79 | 7.02 | 5.73 | 5.45 | 6.08 | 5.53 | 6.28 | 5.24
5.34 | 7.14 | 4.44 | 5.75 | 5.68 | 6.8 | 6.17 | 6.12 | 3.96 | 3.91
4.96 | 6.81 | 6.15 | 4.13 | 6.33 | 5.26 | 5.21 | 3.54 | 8.08 | 6.46
5.42 | 6.44 | 5.83 | 8.61 | 6.22 | 7.06 | 6.81 | 4.95 | 4.6 | 6.71
4.22 | 4.62 | 5.99 | 6.1 | 7.22 | 6.92 | 7.04 | 4.84 | 6.87 | 7.43
6.62 | 4.01 | 5.66 | 5.99 | 8.2 | 6.95 | 8.14 | 4.14 | 5.31 | 4.52
5.69 | 4.99 | 6.22 | 7.34 | 6.98 | 6.54 | 4.37 | 6.48 | 6.28 | 7.28
6.42 | 8.17 | 4.06 | 7.46 | 4.66 | 4.84 | 5.62 | 7.05 | 7.32 | 7.97
6.02 | 3.82 | 4.83 | 5.57 | 5.96 | 5.15 | 7.13 | 5.21 | 7.88 | 4.83
8.17 | 5.94 | 7.16 | 6.57 | 5.71 | 5.48 | 6.33 | 5.12 | 5.66 | 5.42
7.99 | 7.27 | 8.59 | 6.24 | 7.23 | 6.26 | 7.56 | 7.24 | 7.41 | 5.47
4.89 | 5.15 | 4.03 | 4.81 | 7 | 5.49 | 5.17 | 5.6 | 4.45 | 4.29
6.35 | 6.33 | 8.01 | 6.52 | 4.63 | 6.81 | 5.08 | 4.34 | 6.51 | 5.25
3.72 | 4.1 | 4.13 | 7.52 | 4.92 | 6.5 | 4.57 | 6.74 | 4.59 | 6.54
4.55 | 5.67 | 6.56 | 5.97 | 6.55 | 6.67 | 6.54 | 5.47 | 5.95 | 3.61
7.65 | 4.7 | 6.73 | 4.88 | 8.21 | 6.43 | 3.96 | 4.92 | 5.21 | 6.26
5.31 | 4.3 | 5.71 | 4.59 | 7.73 | 5.42 | 5 | 5.52 | 5.68 | 7.67
7.58 | 6.92 | 6.36 | 6.41 | 5.37 | 6.19 | 7.17 | 4.45 | 6.22 | 4.32
6.33 | 3.54 | 5.69 | 6.03 | 5.98 | 7.16 | 6.58 | 8.16 | 4.91 | 6.81
5.96 | 4.21 | 8.13 | 6.67 | 6.41 | 7.78 | 7.95 | 8.01 | 6.56 | 5.34
5.72 | 5.23 | 6.64 | 7.72 | 3.96 | 7.27 | 7.94 | 7.02 | 7.53 | 6.53
6.93 | 6.73 | 6 | 4.12 | 7.84 | 4.32 | 4.53 | 6.87 | 5.14 | 5.28
5.25 | 6.52 | 7.01 | 5.59 | 4.86 | 6.34 | 7.08 | 5.51 | 7.04 | 4.47
5.31 | 5.78 | 8.15 | 7.04 | 3.79 | 7.16 | 6.86 | 8.27 | 4.86 | 5.7
6.54 | 5.94 | 7.26 | 5.56 | 5.58 | 3.91 | 3.25 | 8.17 | 5.02 | 4.95
4.37 | 4.44 | 5.63 | 4.37 | 5 | 6.75 | 7.21 | 6.35 | 3.16 | 5.19
6.66 | 6.12 | 6.27 | 6.36 | 5.5 | 5.98 | 5.56 | 7.87 | 5.15 | 6.86
6.45 | 8.09 | 7.82 | 5.28 | 7.62 | 6.94 | 6.8 | 3.58 | 7.3 | 5.1
6.14 | 7.53 | 6.36 | 6.52 | 5.46 | 5.14 | 5.41 | 4.7 | 6.78 | 6.91
6.1 | 5.18 | 5.45 | 6.67 | 4.01 | 7 | 6.26 | 4.77 | 5.09 | 7.31
5.34 | 6.41 | 8.75 | 6.79 | 4.96 | 6.15 | 7.51 | 6.84 | 4.54 | 8.06
4.33 | 6.36 | 6.27 | 6.54 | 7.52 | 5.93 | 5.39 | 6.77 | 6.7 | 5.99
5.42 | 6.52 | 5.81 | 7.62 | 7.72 | 4.59 | 5.28 | 4.48 | 6.45 | 5.92
6.03 | 8.63 | 4.24 | 5.73 | 6.14 | 7.26 | 4.1 | 4.47 | 5.23 | 7.06
4.28 | 6.07 | 6.4 | 5.53 | 7.35 | 6.22 | 4.88 | 6.36 | 6.2 | 7.37
3.98 | 4.89 | 5.68 | 6.83 | 7.56 | 6.99 | 5.14 | 6.2 | 7.75 | 5.39
3.87 | 4.72 | 5.53 | 3.97 | 6.21 | 5.25 | 6.13 | 5.17 | 5.1 | 5.84
6.19 | 6.61 | 5.14 | 6.48 | 5.89 | 6.07 | 5.25 | 6.5 | 6.08 | 5.94
8.61 | 4.84 | 4.68 | 8.15 | 6.42 | 3.81 | 6.59 | 5.05 | 6.02 | 7.13
6.55 | 7.25 | 5.36 | 4.1 | 7.37 | 5.49 | 7.93 | 4.99 | 6.58 | 8.02
8.32 | 4.8 | 7.28 | 4.53 | 8 | 5.85 | 6.01 | 6.02 | 6.01 | 4.54
5.23 | 5.52 | 5.01 | 4.65 | 7.32 | 7.56 | 8.84 | 6.95 | 5.6 | 4.5
8.22 | 4.92 | 6.1 | 5.88 | 5.29 | 5.56 | 6.04 | 6.22 | 5.71 | 7.66
5.55 | 4.96 | 7.51 | 5.91 | 6.05 | 5.01 | 4.14 | 3.72 | 6.77 | 4.18
7.4 | 6.46 | 5.87 | 6.18 | 8.03 | 4.17 | 5.98 | 7.55 | 6.73 | 7.2
6.21 | 8.84 | 4.02 | 6.15 | 6.98 | 4.15 | 8.49 | 7.12 | 5.32 | 8.39
5.88 | 6.66 | 5.18 | 6.33 | 5.13 | 7.36 | 6.75 | 6.47 | 8.03 | 7.02
6.36 | 5.91 | 5.02 | 5.01 | 4.93 | 4.73 | 3.49 | 5.19 | 5.82 | 5.72
6.08 | 4.42 | 7.1 | 7.76 | 7.36 | 5.51 | 5.3 | 6.26 | 8.27 | 5.03
3.75 | 4.13 | 3.79 | 5.81 | 5.8 | 6.68 | 4.85 | 6.75 | 4.79 | 6.88
6.2 | 4.98 | 6.63 | 7.07 | 6.36 | 6.63 | 4.58 | 8 | 7.25 | 4.03
7.47 | 6.54 | 5.25 | 5.77 | 6.36 | 6.14 | 7.58 | 6.34 | 7.89 | 6.4
7.25 | 6.55 | 5.85 | 7.42 | 4.57 | 5.74 | 6.27 | 4.86 | 7.26 | 4.08
7.13 | 5.53 | 5.31 | 6.22 | 4.73 | 5.12 | 5.74 | 3.76 | 4.96 | 7.6
6.9 | 5.74 | 5.04 | 6.82 | 4.78 | 3.58 | 4.56 | 7.39 | 7.11 | 7.52
6.72 | 3.59 | 5.09 | 3.93 | 7.4 | 6.11 | 4.03 | 4.57 | 5.77 | 6.56
7.8 | 5.89 | 3.82 | 5.03 | 4.17 | 7.38 | 6.22 | 5.73 | 5.52 | 4.26
6.8 | 4.49 | 6.99 | 5.14 | 7.1 | 6.94 | 4.96 | 4.9 | 5.01 | 8.2
6.58 | 6.51 | 5.79 | 6.4 | 5.79 | 8.38 | 5.45 | 5.1 | 8.13 | 5.29
4.47 | 4.75 | 5.8 | 4.29 | 4.72 | 6.89 | 5.92 | 5.32 | 8.21 | 7.49
5.75 | 5.49 | 7.64 | 5.92 | 5.16 | 6.54 | 6.27 | 4.62 | 4.78 | 8.61
6.4 | 8.13 | 6.45 | 6.28 | 5.17 | 5 | 5.69 | 5.24 | 7.43 | 6.46
7.17 | 3.68 | 3.59 | 4.09 | 6.14 | 5.3 | 6.26 | 8.34 | 4.86 | 7.56
5.01 | 5.05 | 4.93 | 6.12 | 6.33 | 4.68 | 4.47 | 5.22 | 4.95 | 6.51
4.14 | 6.64 | 4.9 | 6.94 | 4.87 | 7.99 | 7.9 | 7 | 7.66 | 6.6
6.95 | 7.52 | 6.93 | 5.08 | 8.13 | 5.25 | 4.21 | 6.1 | 6.16 | 4.44
7.82 | 5.68 | 6.67 | 4.2 | 7.17 | 5.59 | 6.07 | 6.28 | 7.28 | 5.17
5.56 | 3.84 | 5.92 | 6.03 | 5.88 | 5.99 | 6.11 | 6.39 | 6.16 | 6.82
7 | 7.35 | 6.26 | 4.62 | 7.17 | 3.37 | 6.82 | 6.45 | 5.78 | 6.23
6.75 | 5.21 | 6.08 | 4.55 | 3.28 | 6.97 | 8.28 | 7.76 | 5.33 | 4.33
6.28 | 6.95 | 5.19 | 4.47 | 6.02 | 6.79 | 4.86 | 5.17 | 6.67 | 6.89
4.56 | 6.08 | 4.81 | 5.17 | 6.37 | 5.37 | 8.42 | 6.44 | 4.77 | 5.07
5.85 | 6.4 | 6.16 | 3.53 | 4.47 | 7.02 | 7.81 | 7.53 | 7.48 | 4.74
4.86 | 4.95 | 4.53 | 6.39 | 6.41 | 7.35 | 6.25 | 4.19 | 3.9 | 6.25
5.57 | 6.07 | 7.77 | 4.87 | 5.52 | 4.99 | 6.44 | 6.96 | 6.14 | 5.62
5.91 | 5.78 | 5.2 | 8.3 | 7.11 | 4.94 | 5.13 | 5.98 | 6.09 | 5.8
4.48 | 4.81 | 5.21 | 6.33 | 5.38 | 6.66 | 6.7 | 7.01 | 8.26 | 5.59
5.94 | 5.89 | 5.6 | 5.52 | 7.31 | 6.11 | 6.69 | 8.02 | 7.06 | 5.71
5.41 | 5.63 | 8.05 | 5.99 | 6.18 | 5.96 | 5.48 | 4.5 | 7.18 | 4.86
3.78 | 5.99 | 3.98 | 5.55 | 6.73 | 6.53 | 5.18 | 4.04 | 5.9 | 3.65
7.72 | 7.65 | 5.72 | 6.87 | 5.11 | 6.22 | 6.71 | 5.39 | 5.19 | 5.43
6.94 | 3.41 | 3.87 | 6.77 | 4.42 | 5.19 | 7.65 | 5.45 | 6.89 | 5.41
3.41 | 7.21 | 7.04 | 7.89 | 7.82 | 4 | 6.67 | 7.07 | 5.07 | 7.1
6.64 | 6.09 | 6.1 | 6.91 | 4.48 | 8.55 | 5.82 | 6.64 | 7.24 | 6
4.58 | 6.05 | 4.34 | 5.41 | 7.95 | 5.64 | 6.95 | 6.14 | 5.84 | 7.53
6.17 | 8.27 | 8.35 | 7.43 | 7.61 | 5.33 | 6.24 | 6.03 | 5.88 | 3.47
5.14 | 5.31 | 4.22 | 6.38 | 3.62 | 5.14 | 5.34 | 4.21 | 6.33 | 6.25
8.27 | 7.43 | 5.29 | 4.47 | 6.96 | 5.15 | 4.26 | 7.2 | 5.48 | 4.32
5.93 | 5.41 | 6.82 | 4.18 | 7.19 | 4.42 | 8.03 | 5.25 | 4.5 | 6.95
4.91 | 6.56 | 5.53 | 5.52 | 6.7 | 7.14 | 4.13 | 5.71 | 4.92 | 6.48
8.39 | 7.94 | 5.03 | 6.16 | 5.69 | 7.62 | 5.72 | 5.7 | 7.54 | 6.01
5.73 | 4.99 | 6.86 | 5.21 | 4.39 | 5.05 | 3.79 | 7.18 | 8.63 | 5.65
7.14 | 7.21 | 7.58 | 7.96 | 8.91 | 8.14 | 5.59 | 6.65 | 6.22 | 4.65
3.62 | 4.94 | 3.31 | 3.92 | 7.39 | 4.83 | 6.47 | 5.32 | 4.22 | 6.9
8.26 | 6.27 | 5.58 | 8.35 | 5.77 | 5.35 | 5.16 | 4.88 | 7.77 | 6.11
3.8 | 7.87 | 5.8 | 6.9 | 5.43 | 5.17 | 6.81 | 6.19 | 5.91 | 3.53
5.12 | 5.17 | 6.07 | 6.89 | 6.27 | 7.32 | 4.04 | 6.12 | 7.16 | 6.66
6.21 | 6.07 | 6.52 | 6.21 | 6.54 | 5.43 | 8.46 | 5.01 | 5.71 | 7.72
5.6 | 6.02 | 6.04 | 5.21 | 7.54 | 6.66 | 5.83 | 7.72 | 5.25 | 6.81
5.61 | 7.82 | 7.52 | 4.61 | 5.42 | 6.99 | 7.27 | 4.68 | 7.17 | 7.46
6.96 | 7.15 | 5.29 | 6.34 | 6.86 | 5.72 | 6.95 | 7.68 | 5.56 | 4.09
3.91 | 6.82 | 6.25 | 4.54 | 7.52 | 4.14 | 5.36 | 6.14 | 3.47 | 6.95
5.2 | 5.68 | 5 | 6.33 | 4.3 | 7.06 | 6.25 | 5.82 | 5.14 | 4.94
6.24 | 4.79 | 5.57 | 6.45 | 6.9 | 4.86 | 7.12 | 3.34 | 6.47 | 5.64
5.34 | 5.73 | 5.76 | 7.87 | 7.01 | 6.58 | 4.47 | 6.1 | 6.5 | 5.54
6.53 | 5.67 | 5.96 | 5.61 | 5.91 | 3.92 | 5.43 | 5.96 | 5.31 | 6.65
3.54 | 6.5 | 4.04 | 6.35 | 7.04 | 7.07 | 4.48 | 4.17 | 6.02 | 5.79
6.76 | 5.82 | 6.79 | 5.08 | 5.25 | 5.57 | 5.16 | 6.61 | 5.66 | 6.58
8.16 | 5.27 | 7.69 | 6 | 6.53 | 6.06 | 5.85 | 5.77 | 5.59 | 8.04
5.8 | 6.78 | 5.91 | 5.8 | 6.23 | 6.2 | 4.01 | 7.34 | 6.12 | 6.77
7.11 | 5.79 | 7.45 | 5.19 | 6.72 | 4.65 | 4.94 | 6.51 | 5.94 | 4.04
6 | 5.74 | 4.87 | 7.5 | 6.78 | 6.7 | 6 | 6.59 | 4.85 | 6.84
6.22 | 6.8 | 6.35 | 6.25 | 7.08 | 4.94 | 7.34 | 4.85 | 7.82 | 5.26
6.4 | 8.3 | 3.94 | 4.97 | 4.37 | 5.35 | 4.6 | 4.13 | 6.81 | 7.7
3.99 | 4.75 | 8.46 | 6.66 | 5.05 | 7.65 | 3.64 | 7.3 | 4.7 | 5.69
7.07 | 6.24 | 5.5 | 4.99 | 3.81 | 8.18 | 6.62 | 6.45 | 4.39 | 6.62
4.95 | 8.26 | 5.26 | 7.86 | 4.28 | 7 | 4 | 7.43 | 7.7 | 8.25
6.52 | 6.77 | 8.06 | 5.2 | 4.89 | 8.2 | 6.34 | 6.37 | 6.34 | 5.58
5.02 | 6.75 | 3.88 | 4.8 | 4.89 | 7.97 | 7.61 | 7.66 | 5.93 | 4.96
8.05 | 8.42 | 7.9 | 6.86 | 7.99 | 4.32 | 8.27 | 6.36 | 5.39 | 7.51
6.43 | 5.01 | 6.1 | 5.71 | 5.74 | 5.41 | 5.01 | 5 | 6.27 | 5.04
5.69 | 4.54 | 4.17 | 6.69 | 7.66 | 7.17 | 7.08 | 7.59 | 8.35 | 4.51
5.81 | 6.34 | 4.92 | 6.58 | 5.34 | 6.21 | 6.01 | 6.05 | 6.46 | 5.89
6.44 | 6.27 | 6.38 | 6.22 | 5.22 | 7.57 | 6.12 | 6.09 | 4.03 | 4.11
4.85 | 5.62 | 4.85 | 5.67 | 5.41 | 4.1 | 7.01 | 3.93 | 4.65 | 7.97
5.3 | 7.89 | 8.63 | 7.94 | 7.65 | 7.53 | 5.67 | 6 | 4.51 | 3.99
6.07 | 4.89 | 4.78 | 6.64 | 8.12 | 3.8 | 7.19 | 7.04 | 8.34 | 6.57
8.42 | 5.12 | 5.54 | 6.71 | 6.34 | 6.73 | 6.94 | 5.98 | 4.01 | 7.4
7.12 | 7.08 | 4.32 | 4.05 | 8.75 | 5.78 | 8.44 | 5.85 | 7.34 | 6.4
5.36 | 6.98 | 7.59 | 4.69 | 5.79 | 4.29 | 8.57 | 6.04 | 7.55 | 7.49
5.97 | 8.47 | 5.95 | 4.92 | 7.44 | 4.11 | 5.38 | 6.93 | 8.19 | 6.2
7.22 | 4.13 | 5.81 | 6.76 | 5.35 | 3.64 | 6.68 | 8.24 | 7.37 | 6.21
7.88 | 7.42 | 6.01 | 7.85 | 6.09 | 5.11 | 3.74 | 5.93 | 5.17 | 6.68
8.72 | 7.01 | 4.81 | 8.42 | 5.75 | 6.2 | 7.16 | 6.8 | 6.33 | 4.4
5.79 | 5.21 | 7.7 | 7.52 | 6.24 | 5.62 | 5.6 | 6.97 | 8.1 | 7.62
6.97 | 5.11 | 6.38 | 5.05 | 4.76 | 7.37 | 6.51 | 5.16 | 4.36 | 5.1
6.74 | 7.64 | 6.72 | 3.39 | 7.44 | 5.63 | 5.12 | 4.74 | 3.82 | 7.3
8.03 | 5.92 | 3.9 | 4.58 | 5.16 | 4.45 | 5.95 | 5.94 | 5.58 | 5.63
7.26 | 4.92 | 7.72 | 5.89 | 6.5 | 6.52 | 4.86 | 6.53 | 7.62 | 6.49
6.14 | 3.21 | 5.26 | 3.99 | 7.69 | 6.07 | 7.22 | 5.71 | 5.42 | 8.15
6.27 | 5.51 | 6.04 | 4.66 | 4.56 | 7.33 | 7.53 | 7.72 | 7.83 | 5.73
5.01 | 6.67 | 5.52 | 6.88 | 7.28 | 7.46 | 4.32 | 5.49 | 3.78 | 6.17
5.03 | 5.63 | 4.74 | 8.49 | 5.39 | 6.78 | 6.28 | 5.09 | 8.09 | 4.57
4.2 | 4.64 | 6.68 | 7.55 | 7.14 | 6.48 | 6.7 | 6.05 | 6.97 | 5.33
4.74 | 6.61 | 5.16 | 6.13 | 7.58 | 4.87 | 4.28 | 3.31 | 5.97 | 7.92
7.24 | 6.2 | 4.33 | 5.68 | 5.4 | 4.49 | 6.38 | 7.33 | 7.57 | 5.83
5.05 | 6.49 | 5.99 | 7.45 | 7.06 | 6.45 | 6.1 | 8.91 | 5.05 | 6.65
5.14 | 4.25 | 4.2 | 4.73 | 5.97 | 4.4 | 4.15 | 5.48 | 4.74 | 3.86
5.01 | 3.76 | 4.91 | 3.64 | 7.71 | 8.36 | 5.98 | 5.54 | 5.46 | 8.08
3.61 | 5.59 | 6.66 | 7.04 | 5.03 | 7.56 | 6.21 | 6.82 | 4.53 | 5.39
5.48 | 6.47 | 7.11 | 7.28 | 4.48 | 6.92 | 6.12 | 5.49 | 5.54 | 7.04
6.47 | 5.24 | 6 | 6.37 | 5.5 | 5.74 | 3.37 | 5.25 | 5.82 | 6.02
5.66 | 5.59 | 5.75 | 4.78 | 8.31 | 5.67 | 5.12 | 5.35 | 4.75 | 5.76
4.77 | 8.25 | 5.39 | 8.13 | 7.75 | 6.72 | 6.66 | 4.7 | 6.4 | 6.16
4.03 | 7.64 | 5.32 | 6.08 | 4.98 | 6.2 | 5.63 | 6.81 | 8.69 | 6.71
4.4 | 4.95 | 5.32 | 5.34 | 6.08 | 5.68 | 6.83 | 7.36 | 6.64 | 4.92
6.98 | 4.43 | 5.67 | 7.81 | 5.48 | 6.16 | 4.09 | 3.9 | 6.69 | 6.1
7.21 | 6.82 | 5.3 | 6.88 | 8.26 | 6.45 | 5.23 | 5.68 | 6.54 | 7.5
7.42 | 5.17 | 4.21 | 5.39 | 7.07 | 6.15 | 4.9 | 6.55 | 5.37 | 6.25
5.59 | 6.93 | 4.69 | 7.5 | 4.51 | 5.13 | 7.46 | 4.93 | 8.79 | 6.83
5.94 | 5.93 | 5.98 | 4.41 | 5.56 | 5.86 | 4.44 | 5.86 | 5.8 | 6.85
7.86 | 8.61 | 3.51 | 6.41 | 8.49 | 6.81 | 4.38 | 4.61 | 6.37 | 5.66
6.59 | 6.33 | 4.17 | 6.83 | 5.73 | 6.35 | 7.24 | 7.41 | 7.52 | 5.95
5.49 | 6.43 | 6.37 | 7.35 | 7.75 | 4.6 | 5.77 | 6.03 | 6.69 | 7.71
5.71 | 5.52 | 4.93 | 4.2 | 5.21 | 7.17 | 7.62 | 4.67 | 8.53 | 6.45
6.08 | 4.03 | 6.44 | 6.17 | 6.09 | 8.19 | 6.83 | 4.45 | 6.1 | 7.09
3.82 | 5.84 | 8.3 | 8.21 | 6.19 | 7.5 | 7.69 | 5.19 | 6.48 | 6.05
7.74 | 7.53 | 7.68 | 6.56 | 5.19 | 4.97 | 5.05 | 4.88 | 3.85 | 3.69
8.09 | 7.09 | 4.51 | 5.55 | 7.91 | 4.25 | 5.86 | 4.2 | 5.03 | 4.17
7.93 | 8.39 | 5.56 | 6.79 | 6.48 | 5.53 | 5.71 | 5.08 | 7.45 | 5.59
6.71 | 5.98 | 5.43 | 5.72 | 7.46 | 6.18 | 8.26 | 3.43 | 5.94 | 7.57
3.94 | 5.19 | 4.37 | 5.24 | 6.01 | 7.51 | 5.05 | 4.91 | 6.07 | 7.25
7.38 | 7.34 | 6.81 | 7.31 | 7.08 | 6.69 | 5.78 | 4.94 | 7.31 | 4.21
5.51 | 6.87 | 5.13 | 6.92 | 5.59 | 7.41 | 8.01 | 6.65 | 5.81 | 7.31
5.42 | 5.5 | 4.77 | 7.03 | 7.19 | 6.33 | 5.52 | 5.95 | 5.86 | 3.31
5.49 | 5.65 | 6.53 | 8.72 | 3.16 | 5.85 | 5.2 | 6.9 | 4.45 | 5.86
4.45 | 4.87 | 5.15 | 5.26 | 5.72 | 5.41 | 8.69 | 6 | 6.96 | 4.79
8.13 | 5.5 | 6.86 | 5.42 | 6.04 | 6.57 | 7.58 | 6.08 | 4.98 | 6.74
5.11 | 6.25 | 5.55 | 5.85 | 5.61 | 7.63 | 3.39 | 4.65 | 7.27 | 5.63
6.09 | 3.53 | 7.34 | 6.7 | 5.01 | 5.47 | 4.59 | 7.33 | 6.12 | 5.27
8.35 | 3.61 | 5 | 7.33 | 6.62 | 5.63 | 5.08 | 6.14 | 6.8 | 4.23
6.33 | 5.02 | 4.2 | 7.41 | 6.59 | 4.9 | 7.88 | 5.44 | 3.8 | 6.68
6 | 6.06 | 7.62 | 6.69 | 5.02 | 5.98 | 7.49 | 7.11 | 3.65 | 6.8
3.7 | 6.95 | 5.53 | 5.01 | 3.37 | 7.28 | 5.81 | 5.26 | 7.22 | 6.66
7.16 | 4.36 | 7.28 | 7.64 | 7.15 | 4.18 | 3.97 | 5.88 | 6.28 | 5.85
5.78 | 4.91 | 5.19 | 5.63 | 5.78 | 6.16 | 3.83 | 6.58 | 7.34 | 4.28
4.93 | 5.35 | 4.7 | 6.05 | 5.32 | 7.05 | 5.56 | 3.89 | 3.09 | 5.14
7.46 | 4.77 | 5.75 | 8.06 | 8.39 | 5.02 | 6.58 | 5.22 | 5.7 | 6.2
6.18 | 5.29 | 6.05 | 5.24 | 6.81 | 5.81 | 6.19 | 4.5 | 6.47 | 4.62
5.66 | 5.14 | 6.03 | 5.56 | 4.09 | 7.77 | 6.48 | 4.68 | 5.88 | 6.47
5.59 | 6.01 | 7.37 | 3.37 | 5.34 | 4.56 | 7.02 | 6.32 | 5.16 | 6.08
6.1 | 5.07 | 6.85 | 7.74 | 4.58 | 4.82 | 6.16 | 6.2 | 4.74 | 3.97
6.74 | 8.41 | 5.12 | 6.8 | 4.23 | 5 | 5.5 | 6.54 | 5.29 | 6.89
6.1 | 6.6 | 6.08 | 3.69 | 6.17 | 7.53 | 5.99 | 6.49 | 6.39 | 4.48
7.14 | 5.88 | 6.97 | 3.62 | 7.21 | 7.34 | 6.79 | 6.48 | 4.02 | 4.83
3.09 | 5.83 | 4.53 | 7.06 | 6.11 | 8.79 | 6.27 | 4 | 6.14 | 6.38
6.05 | 4.83 | 5.48 | 6.2 | 4 | 7.87 | 4.33 | 6.5 | 7.28 | 8.05
6.73 | 4.73 | 5.41 | 3.09 | 6.18 | 6.68 | 5.67 | 6.63 | 6.81 | 6.24
8.47 | 5.85 | 6.91 | 4.42 | 6.63 | 4.84 | 5.44 | 7.03 | 6.17 | 6.61
7.91 | 6.45 | 6.51 | 3.65 | 5.93 | 6.03 | 6.18 | 6.55 | 4.54 | 6.16
5.58 | 4.16 | 5.21 | 4.13 | 7.83 | 4.33 | 7.59 | 7.01 | 4.47 | 7.69
5.53 | 7.04 | 4.36 | 6.14 | 7.16 | 5.9 | 5.31 | 4.47 | 7.93 | 8.1
7.01 | 5.33 | 4.01 | 5.31 | 4.41 | 8.09 | 7.34 | 6.41 | 6.44 | 6.9
6.23 | 4.72 | 3.93 | 6.59 | 6.87 | 5.75 | 5.55 | 6.53 | 3.76 | 3.95
5.63 | 3.78 | 3.78 | 4.25 | 8.1 | 5.6 | 8.24 | 7.19 | 4.52 | 5.97
5.8 | 6.28 | 5.85 | 6.77 | 7.18 | 8.51 | 5.66 | 5.67 | 6.77 | 4.38
5.39 | 7.14 | 6.76 | 5.18 | 6.6 | 6.37 | 8.17 | 7.15 | 5.08 | 8.91
7.3 | 5.13 | 7.88 | 5.67 | 4.95 | 5.7 | 4.74 | 6.08 | 5.29 | 4.73
5.25 | 7.3 | 6.32 | 5.48 | 6 | 7.02 | 7.07 | 6.85 | 4.62 | 6.12
4 | 5.73 | 6.69 | 6.43 | 4.4 | 7.62 | 6.25 | 6.4 | 5.8 | 6.39
4.57 | 5.34 | 5.41 | 6.17 | 6.67 | 4.53 | 6.6 | 8.38 | 4.89 | 7.19
6.61 | 6.1 | 6.19 | 5.47 | 6.92 | 8.21 | 7.09 | 3.56 | 7.56 | 5.52
4.25 | 7.83 | 5.85 | 6.35 | 7.5 | 6.71 | 5.36 | 7.46 | 4.29 | 7.77
5.28 | 7.54 | 4.72 | 7.66 | 5.6 | 7.27 | 5.88 | 6.92 | 7.12 | 6.99
6.42 | 8.01 | 4.99 | 6.85 | 6.68 | 5.44 | 4.64 | 5.79 | 6.36 | 4.25
6.46 | 6.39 | 3.45 | 5.05 | 8.59 | 4.38 | 7.98 | 6.38 | 4.09 | 6.05
7.35 | 6.03 | 6.25 | 6.2 | 5.45 | 4.28 | 7.73 | 5.31 | 6.37 | 6.56
5.28 | 7 | 5.94 | 6.25 | 5.55 | 4.79 | 7.39 | 5.83 | 4.76 | 5.78
7.09 | 7.72 | 7.01 | 6.99 | 5.23 | 6.64 | 6.63 | 5.05 | 6.83 | 6.55
6.87 | 6.53 | 5.31 | 3.95 | 5.91 | 6.36 | 3.58 | 7.55 | 7.26 | 7
8.46 | 4.65 | 6.07 | 3.83 | 4.96 | 6.76 | 5.9 | 5.8 | 8.24 | 5.82
7.92 | 6.11 | 5.96 | 4.88 | 5.37 | 5.65 | 4.38 | 8.47 | 6.67 | 5.9
6.08 | 6.12 | 6.09 | 4.62 | 7.18 | 5.7 | 6.92 | 7.42 | 4.66 | 4.96
3.88 | 6.25 | 4.62 | 5.78 | 5.07 | 6.19 | 8.47 | 5.65 | 7.53 | 7.35
7.75 | 6.48 | 3.34 | 5.79 | 5.61 | 6.03 | 4.03 | 4.77 | 3.58 | 5.5
7.66 | 6.65 | 5.1 | 5.66 | 8.17 | 4.97 | 6.36 | 5.5 | 5.27 | 5.48
6.62 | 6.12 | 7 | 8.22 | 7.83 | 5.39 | 6.77 | 3.37 | 5.57 | 7.18
5.7 | 6.89 | 6.95 | 5.33 | 4.44 | 7.44 | 5.57 | 7.99 | 6.72 | 5.85
6.81 | 8.12 | 6.03 | 5.2 | 3.78 | 4.95 | 5.81 | 4.06 | 4.4 | 5.29
6.18 | 5.06 | 7.09 | 4.32 | 6.39 | 5.65 | 5.48 | 6.92 | 4.84 | 7.62
6.59 | 6.74 | 6.48 | 7.32 | 5.05 | 7.75 | 7.66 | 3.98 | 4.87 | 7.34
5.21 | 4.82 | 8.28 | 7.14 | 5.14 | 4.85 | 6.33 | 7.7 | 4.97 | 4.31
7.05 | 5.25 | 5.4 | 4.5 | 5.83 | 4.34 | 6.02 | 5.15 | 5.19 | 4.01
6.39 | 6.92 | 4.8 | 6.72 | 8.41 | 6.17 | 6.58 | 5.96 | 6.67 | 4.71
4.54 | 7.62 | 5.42 | 5.04 | 7.62 | 7.15 | 5.92 | 5.47 | 5.66 | 5.01
7.18 | 4.93 | 4.58 | 5.7 | 5.53 | 6.44 | 8.32 | 5.61 | 5.51 | 7.12
6.69 | 4.76 | 3.69 | 6.99 | 6.33 | 7.68 | 5.66 | 6 | 5.12 | 7.42
5.24 | 7.34 | 6.12 | 5.47 | 6.25 | 7.97 | 5.93 | 6.13 | 4.7 | 6.57
8.38 | 5.46 | 6.01 | 5.57 | 5.25 | 7.2 | 5.32 | 7.4 | 3.51 | 5.64
6.71 | 4.86 | 5.44 | 4.02 | 4.72 | 4.54 | 7.04 | 5.78 | 7.37 | 5.15
4.42 | 5.64 | 5.14 | 5.75 | 6.12 | 4.89 | 7.05 | 6.75 | 8.14 | 5.08
7.73 | 8.07 | 7.19 | 4.85 | 6.92 | 5.82 | 5.37 | 4.44 | 6.18 | 7.04
5.69 | 5.01 | 6.28 | 7.29 | 7.21 | 6.87 | 8.34 | 5.71 | 4.28 | 7.03
4.88 | 5.9 | 5.42 | 3.54 | 4.7 | 7.85 | 6.79 | 6.52 | 7.35 | 4.51
7.49 | 5.62 | 4.57 | 3.7 | 7.05 | 5.87 | 6.55 | 5.97 | 6.08 | 6.54
7.02 | 5.67 | 5.84 | 7.8 | 3.21 | 5.32 | 4.9 | 6.12 | 6.21 | 8.26
5.29 | 7.16 | 5.72 | 4.84 | 6.65 | 5.33 | 3.86 | 4.17 | 4.43 | 5.05
4.61 | 5.7 | 6.02 | 6.48 | 8.53 | 8.39 | 5.3 | 4.39 | 4.65 | 7.94
5.29 | 5.97 | 6.51 | 6.77 | 6.87 | 5.02 | 6.23 | 5.97 | 6.95 | 6.41
6.83 | 7.03 | 5.35 | 4.44 | 8.55 | 3.82 | 4.54 | 5.63 | 4.68 | 5.31
7.69 | 7.11 | 7.11 | 7 | 7.1 | 4.92 | 6.51 | 5.78 | 6.23 | 4.37
5.41 | 4.12 | 5.87 | 7.2 | 4.9 | 5.59 | 5.95 | 5.23 | 6.95 | 6.76
6.88 | 6.41 | 5.49 | 4.89 | 8.63 | 8.15 | 5.06 | 5.2 | 6.03 | 5.83
6.87 | 7.02 | 6.37 | 6.28 | 6.88 | 3.79 | 4.51 | 7.98 | 5.64 | 3.84
6.54 | 6.22 | 5.83 | 7.11 | 5.31 | 6.82 | 6.93 | 5.73 | 6.07 | 6.42
7.31 | 6.86 | 5.77 | 4.64 | 6.76 | 5.19 | 7.68 | 7.1 | 6.71 | 7.91
5 | 6.09 | 5.14 | 6.7 | 6.57 | 7.03 | 5.36 | 6.25 | 6.79 | 6.91
6.32 | 4.63 | 7.75 | 8.55 | 5.19 | 5.77 | 8.75 | 6.17 | 6.35 | 4.98
4.36 | 5.49 | 7.02 | 5.94 | 6.25 | 8.16 | 7.54 | 6.24 | 5.92 | 6.01
7.91 | 7.7 | 5.75 | 7.66 | 5.09 | 5.09 | 7.7 | 5.75 | 4.96 | 6.21
5.26 | 5.16 | 4.55 | 7.17 | 3.91 | 8.35 | 4.97 | 7.35 | 5.84 | 7.64
6.67 | 7.47 | 6.11 | 4.9 | 8.66 | 4.6 | 6.85 | 5.67 | 6.2 | 8.51
5.33 | 5.16 | 3.21 | 5.07 | 3.31 | 5.23 | 6.77 | 5.83 | 5.91 | 4.85
5.09 | 5.93 | 7.23 | 7 | 3.74 | 6.4 | 5.21 | 4.57 | 8.59 | 7.32
6.8 | 7.23 | 5.5 | 5.86 | 6.95 | 5.93 | 5.27 | 6.18 | 7.94 | 5.95
6.22 | 6.84 | 6.16 | 7.53 | 4.81 | 3.31 | 5.99 | 3.96 | 7.47 | 6.41
6.9 | 6.69 | 5.27 | 4.34 | 6.45 | 5.79 | 6.38 | 4.15 | 4.12 | 6.73
5.82 | 6.9 | 6.09 | 8.28 | 8.61 | 6.14 | 7.33 | 7.23 | 3.61 | 8.47
4.87 | 6.66 | 6.44 | 4.16 | 6.8 | 5.46 | 7.5 | 5.72 | 5.17 | 3.45
5.31 | 7.72 | 4.83 | 7.37 | 5.14 | 5.31 | 7.97 | 3.25 | 5.72 | 4.49
5.87 | 7.4 | 4.73 | 5.22 | 7.77 | 7.75 | 4.53 | 7.08 | 7.4 | 8.12
8.1 | 4.23 | 5.31 | 7.77 | 4.77 | 4.81 | 6.45 | 4.69 | 4.32 | 5.7
7.47 | 5.98 | 6.19 | 7.53 | 4.57 | 6.14 | 5.55 | 6.75 | 6.43 | 6.61
3.49 | 7.88 | 4.41 | 5.46 | 5.65 | 5.87 | 5.97 | 7.47 | 6.69 | 7.15
4.69 | 5.66 | 7.32 | 4.71 | 6.77 | 5.17 | 7.85 | 5.29 | 4.28 | 6.66
6.44 | 7.05 | 4.67 | 5.96 | 6.01 | 5.66 | 5.29 | 4.73 | 7.79 | 6.03
5.05 | 3.56 | 6.46 | 6.16 | 7.91 | 6.38 | 7.55 | 6.2 | 5.26 | 5.23
3.69 | 4.48 | 7.17 | 3.89 | 4.2 | 5.38 | 3.7 | 5.26 | 5.84 | 8.07
5.75 | 6.85 | 6.41 | 5.71 | 5.63 | 6.76 | 3.82 | 3.92 | 6.99 | 6.22
6.04 | 8 | 5.95 | 8.03 | 5.47 | 6.25 | 7.36 | 7.85 | 3.88 | 8.49
6.92 | 5.41 | 7.26 | 4.82 | 5.97 | 6.25 | 5.32 | 5.73 | 6.75 | 3.51
6.23 | 7.08 | 7.22 | 6.09 | 5.78 | 4.36 | 7.01 | 5.49 | 5.55 | 5.36
6.16 | 5.38 | 4.84 | 8.66 | 4.39 | 4.39 | 6.34 | 5.11 | 5.8 | 7.02
6.51 | 5.35 | 6.15 | 6.81 | 6.54 | 6.23 | 6.11 | 5.99 | 5.97 | 6.98
7.36 | 7.48 | 6.83 | 5.74 | 7.74 | 6.65 | 4.55 | 5.1 | 4.94 | 6.33
7.26 | 6.68 | 7.07 | 5.06 | 6.04 | 5.06 | 7.44 | 7.07 | 3.79 | 5.46
5.99 | 4.36 | 5.88 | 5.84 | 4.61 | 5.21 | 3.28 | 3.65 | 6.65 | 5.3
8.28 | 7.11 | 8.26 | 6.21 | 5.26 | 3.34 | 5.54 | 4.62 | 7.8 | 5.47
8.55 | 7.58 | 4.28 | 6.96 | 3.43 | 4.48 | 3.88 | 8.12 | 5.97 | 7.45
8 | 6.44 | 6.45 | 5.87 | 5.82 | 6.03 | 7.52 | 6.79 | 6.65 | 6.27
4.31 | 5.55 | 3.39 | 3.78 | 5.52 | 4.37 | 4.92 | 7.62 | 4.53 | 4.17
5.93 | 7.42 | 5.44 | 6.65 | 6.01 | 4.7 | 3.99 | 4.52 | 7.74 | 6.06
5.73 | 7.51 | 4.54 | 4.63 | 8.57 | 4.13 | 5.24 | 7.11 | 3.97 | 5
6.03 | 8.19 | 6.39 | 6.73 | 3.09 | 5.83 | 5.03 | 8.03 | 5.74 | 8.3
6.06 | 5.12 | 7.49 | 7.23 | 6.64 | 4.76 | 7.16 | 6.37 | 8.46 | 6.13
5.58 | 8.18 | 3.72 | 4.4 | 5.85 | 4.55 | 8.18 | 6.86 | 5.83 | 7.38
6.64 | 7.31 | 5.3 | 5.64 | 6.02 | 6.62 | 7.84 | 5.4 | 7.58 | 7.41
8.84 | 5.43 | 7.31 | 7.44 | 6.2 | 5.59 | 7.47 | 6.55 | 5.79 | 5.45
6.15 | 5.44 | 7.93 | 4.23 | 5.52 | 6.66 | 8.55 | 6.24 | 6.42 | 6.24
6.63 | 6.32 | 5.86 | 5.96 | 6.46 | 7.52 | 6.47 | 3.41 | 7.55 | 5.17
7.59 | 5.79 | 5.07 | 8.53 | 8.16 | 7.31 | 7.75 | 8.49 | 6.18 | 5.34
5.17 | 8.15 | 6.28 | 6.61 | 3.99 | 6.4 | 8.39 | 5.55 | 5.1 | 7.66
5.71 | 8.02 | 5.43 | 6.67 | 3.83 | 6.34 | 6.46 | 4.59 | 5.76 | 6.07
5.93 | 5.6 | 5.97 | 5.36 | 3.86 | 6.39 | 4.89 | 6.25 | 6.38 | 4.73
5.47 | 4.5 | 4.66 | 6.37 | 6.42 | 7.61 | 8.21 | 3.78 | 7.15 | 6.16
4.7 | 5.63 | 8.69 | 7.11 | 7.55 | 6.18 | 4.19 | 6.74 | 5.47 | 3.16
5.04 | 6.17 | 6.79 | 6.78 | 6.14 | 6.37 | 6.5 | 6.71 | 6.91 | 5.84
5.66 | 5.08 | 5.09 | 7.18 | 3.68 | 6.33 | 5.22 | 6.73 | 6.06 | 5.78
7.15 | 5.8 | 5.71 | 5.25 | 7.2 | 6.64 | 4.51 | 5.28 | 6.52 | 6.1
5.86 | 4.91 | 7.92 | 6.55 | 6.91 | 8.59 | 5.35 | 5.45 | 3.86 | 5.69
6.62 | 4.37 | 4.96 | 5.44 | 4.87 | 8.41 | 6.08 | 8.61 | 5.57 | 4.98
7.39 | 4.15 | 6.5 | 8.17 | 4.74 | 3.54 | 7.37 | 8.44 | 3.34 | 6.78
6.99 | 6.38 | 7.06 | 6.22 | 5.36 | 5.36 | 6.67 | 4.51 | 6.76 | 5.02
7.17 | 7.04 | 7.79 | 5.76 | 6.32 | 6.55 | 5.83 | 4.29 | 5.56 | 6.03
7.72 | 6.57 | 6.06 | 5.83 | 5.15 | 5.71 | 8.09 | 6.7 | 7.35 | 5.84
5.73 | 5.68 | 4.75 | 5.74 | 4.77 | 7.08 | 5.53 | 5.14 | 6.01 | 7.55
5.55 | 5.2 | 5.39 | 5.6 | 8.22 | 5.25 | 6.77 | 4.91 | 6.6 | 7.83
6.81 | 6.11 | 5.92 | 6.95 | 6.15 | 8.1 | 4.29 | 6.85 | 5.74 | 8.53
5.72 | 4.11 | 5.49 | 5.34 | 6.89 | 6.75 | 5.27 | 4.8 | 6.68 | 6.04
6.03 | 7.17 | 6.66 | 6.42 | 7.38 | 6.9 | 5.14 | 5.3 | 6.89 | 5.57
6.59 | 6.88 | 6.26 | 7.68 | 5.75 | 6.25 | 4.94 | 4.2 | 5.22 | 6.28
4.18 | 6 | 6.09 | 7.47 | 4.99 | 5.67 | 7.11 | 6.06 | 5.49 | 4.81
6.22 | 7.13 | 6.52 | 5.09 | 4.97 | 3.96 | 6.6 | 6.6 | 6.09 | 4.84
6.44 | 4.78 | 3.25 | 5.7 | 4.08 | 6.13 | 6.15 | 7.46 | 5.38 | 6.72
4.88 | 3.95 | 6.87 | 3.98 | 5.76 | 6.62 | 8.13 | 6.11 | 5.42 | 6.11
5.89 | 5.41 | 6.99 | 6.83 | 4.35 | 5.36 | 7.1 | 8.53 | 7.23 | 6.5
4.32 | 5.58 | 8.16 | 4.97 | 6.43 | 6.26 | 5.9 | 5.11 | 7.91 | 5.78
4.03 | 6.2 | 7.11 | 7.31 | 3.56 | 6.51 | 8.22 | 4.9 | 7.95 | 6.28
6.83 | 7.13 | 4.94 | 6.15 | 4.19 | 5.04 | 5.79 | 6.02 | 6.36 | 5.31
8.08 | 6.74 | 6.97 | 4.72 | 4.21 | 5.27 | 4.73 | 5.24 | 5.12 | 4.96
5.38 | 7.95 | 4.25 | 7.98 | 6.03 | 7.12 | 5.14 | 7.65 | 6.61 | 5
7.2 | 6.12 | 6.2 | 5.84 | 5.36 | 6.61 | 3.56 | 6.46 | 6.33 | 6.09
6.37 | 4.73 | 6.85 | 5.23 | 4.34 | 4.85 | 4.88 | 5.38 | 7.87 | 4.62
5.89 | 7.18 | 8.19 | 6.01 | 5.42 | 6.1 | 4.67 | 7.12 | 6.87 | 5.83
7.35 | 6.16 | 5.51 | 4.48 | 7.47 | 8.47 | 7.91 | 8.18 | 6.89 | 4.81
6.45 | 6.38 | 8.39 | 4.39 | 5.3 | 5.4 | 4.81 | 6.07 | 5.52 | 3.82
4.26 | 5.49 | 5.49 | 5.77 | 4.66 | 5.44 | 6.45 | 5.75 | 7.16 | 4.54
6.67 | 5.8 | 4.47 | 6.08 | 4.49 | 6.58 | 6.18 | 6.72 | 7.19 | 5.6
8.44 | 7.06 | 8.08 | 5.95 | 6.14 | 5.84 | 5.29 | 6.18 | 5.77 | 7.76
8.06 | 5.21 | 6.11 | 6.36 | 5.47 | 3.21 | 7.8 | 3.79 | 5.75 | 5.06
7.98 | 6.35 | 6.34 | 4.94 | 6.75 | 3.65 | 6.74 | 7.13 | 5.92 | 4
4.51 | 5.23 | 5.6 | 4.25 | 4.94 | 5.8 | 4.93 | 6.28 | 3.89 | 5.37
3.56 | 5.6 | 7.12 | 5.98 | 6.21 | 8.63 | 5.88 | 7.35 | 5.13 | 5.09
6.16 | 6.83 | 6.62 | 3.28 | 6.58 | 5.2 | 4.99 | 5.61 | 6.4 | 5.65
8.41 | 8.69 | 8.84 | 5.94 | 7.77 | 6.93 | 6.64 | 5.87 | 6.82 | 4.36
7.67 | 6.96 | 4.28 | 6.62 | 6.44 | 3.62 | 6.85 | 5.92 | 5.36 | 8.79
4.92 | 5.56 | 6.64 | 6.36 | 5.21 | 7.07 | 6.42 | 6.44 | 6.41 | 6.13
6.43 | 5.99 | 5.05 | 6.51 | 6.71 | 6.37 | 5.65 | 5.55 | 8.28 | 6.62
5.91 | 5.69 | 5.69 | 6.23 | 7.31 | 3.83 | 6.2 | 5.23 | 5.3 | 7.36
6.34 | 7.63 | 6.41 | 6.34 | 6.13 | 6.56 | 6.18 | 6.4 | 6.98 | 4.39
4.97 | 4.62 | 3.61 | 6.55 | 6.09 | 5.99 | 7.49 | 4.35 | 8.12 | 7.38
5.22 | 6.35 | 8.09 | 5.12 | 5.66 | 7.11 | 6.01 | 7.15 | 5.7 | 4.82
5.63 | 7 | 4.69 | 5.49 | 5.26 | 5.03 | 5 | 6.26 | 5.67 | 7.83
6.79 | 6.14 | 5.74 | 5.97 | 3.87 | 3.69 | 7.22 | 4.28 | 6.1 | 5.18
6.69 | 5.11 | 7.12 | 4.74 | 6.16 | 7.3 | 6.96 | 4.27 | 4.46 | 6.52
5.68 | 4.94 | 5.23 | 5.23 | 6.28 | 6.51 | 4.24 | 7.04 | 5.86 | 4.87
4.9 | 6.42 | 6.13 | 4.95 | 4.78 | 7.32 | 4.76 | 3.68 | 5 | 6.12
6.61 | 6.22 | 6.03 | 5.61 | 3.93 | 6.24 | 6.16 | 4.53 | 8.04 | 5.42
6.48 | 6.95 | 4.98 | 5.13 | 4.32 | 3.99 | 4.23 | 4.64 | 5.9 | 6.07
6.6 | 4.98 | 6.75 | 6.44 | 6.36 | 5.04 | 6.84 | 5.16 | 5.83 | 6.13
4.44 | 4.96 | 7.77 | 5.69 | 6.82 | 6.42 | 6.99 | 8.11 | 5.79 | 7.8
6.51 | 5.1 | 5.34 | 6.06 | 7.88 | 7.49 | 7 | 4.66 | 5.48 | 6.03
4.04 | 7.75 | 5.23 | 6.59 | 5.12 | 5.6 | 8.08 | 7.52 | 5.36 | 6.28
5.6 | 4.93 | 6.42 | 7.34 | 5.8 | 6.64 | 5.31 | 4.76 | 5.69 | 4.69
5.1 | 7.66 | 6.57 | 5.62 | 3.69 | 5.38 | 7.06 | 7.92 | 7.1 | 5.53
6.89 | 6.26 | 4.72 | 5.4 | 7.53 | 4.35 | 7.41 | 7.44 | 4.19 | 5.29
6.04 | 6.36 | 5.93 | 4.28 | 6.06 | 6.8 | 4.25 | 6 | 3.21 | 5.44
4.7 | 7.06 | 6.88 | 6.66 | 5.77 | 3.73 | 6.03 | 4.74 | 5.76 | 4.72
6.47 | 6.79 | 6.63 | 8.07 | 4.36 | 4.5 | 7.11 | 5.07 | 5.59 | 5.4
8.3 | 5.29 | 3.97 | 7.47 | 6.91 | 5.14 | 6.78 | 5.79 | 4.82 | 3.83
7.06 | 6.98 | 6.66 | 6.68 | 4.6 | 6.1 | 4.7 | 4.92 | 3.68 | 6.75
5.51 | 6.21 | 8.79 | 3.58 | 5.4 | 6.07 | 6.52 | 6.42 | 6.16 | 4.97
7.55 | 5.64 | 8.55 | 8.39 | 5.68 | 4.75 | 5.59 | 6.51 | 5.86 | 5.03
5.5 | 7.69 | 5.66 | 7.28 | 6.2 | 5.88 | 7.42 | 3.64 | 7.24 | 5.88
6.91 | 6.69 | 5.98 | 4.98 | 5.27 | 5.66 | 4.11 | 4.65 | 4.57 | 6.41
8.36 | 6.37 | 6.77 | 6.92 | 7.79 | 6.12 | 6.07 | 6.79 | 4.8 | 6.7
6.55 | 7.45 | 6.27 | 6.34 | 5.84 | 7.83 | 8.16 | 6.54 | 6.55 | 3.43
5.95 | 7.44 | 6.62 | 6.21 | 5.53 | 4.8 | 6.86 | 4.79 | 3.75 | 6.2
4.5 | 4.59 | 6.47 | 6.37 | 5.41 | 6.35 | 6.16 | 5.12 | 8.47 | 5.3
6.37 | 6.94 | 7.13 | 6.5 | 5.97 | 4.22 | 8.59 | 6.15 | 6.26 | 7.29
4.48 | 6.37 | 6.59 | 6.45 | 6.34 | 5.89 | 3.16 | 4.75 | 4.82 | 6.63
4.84 | 3.98 | 7.19 | 6.26 | 6.52 | 3.88 | 5.61 | 7.6 | 7.29 | 4.56
7.97 | 5.37 | 6.92 | 6.07 | 6.69 | 6.65 | 4.8 | 6.21 | 4.76 | 6.28
7.68 | 7.35 | 4.48 | 3.76 | 6.85 | 7.13 | 6.39 | 6.98 | 5.85 | 5.74
5.35 | 5.83 | 8.18 | 5.48 | 6.52 | 6.95 | 5.65 | 7.43 | 3.49 | 5.54
3.81 | 5.9 | 6.25 | 5.13 | 6.57 | 6.15 | 6.61 | 5.52 | 4.97 | 3.9
7.52 | 7.31 | 5.33 | 4.17 | 6.25 | 7.04 | 5.59 | 6.12 | 4.89 | 6.49
7.34 | 6.87 | 7 | 6.58 | 7.97 | 8.91 | 6.5 | 6.01 | 6.48 | 6.34
5.96 | 4.48 | 7.03 | 7.93 | 5.24 | 4.88 | 7.32 | 7.7 | 4.31 | 6.84
4.34 | 5.88 | 6.6 | 7.51 | 6.27 | 4.67 | 5.6 | 4.96 | 8.51 | 6.12
6.28 | 5.1 | 6.18 | 5.19 | 6.17 | 5.42 | 4.77 | 6.24 | 6.92 | 5.76
3.31 | 6.55 | 5.56 | 6.91 | 6.4 | 5.3 | 4.62 | 7.38 | 5.64 | 6.53
5.36 | 7.19 | 7.94 | 6.49 | 6.73 | 5.48 | 6.89 | 5.36 | 6.18 | 6.46
3.73 | 5.6 | 5.94 | 6.07 | 5.64 | 5.11 | 6.39 | 3.16 | 6.58 | 4.78
6.68 | 7.2 | 5.64 | 5.82 | 3.25 | 8.44 | 4.7 | 5.8 | 7.58 | 6.59
6.36 | 5.42 | 5.95 | 5.58 | 7.24 | 5.52 | 5.19 | 5.48 | 5.53 | 5.82
6.49 | 5.45 | 5.7 | 5.55 | 6.94 | 4.5 | 7.97 | 6.7 | 4.08 | 4.4
7.33 | 6.15 | 8.14 | 6.25 | 6.71 | 6.45 | 5.74 | 5.53 | 7.84 | 4.24
8.19 | 5.77 | 4.87 | 7.24 | 8.84 | 8.26 | 4.98 | 7.17 | 5.4 | 6.18
6.17 | 4.39 | 6.22 | 6.32 | 5.84 | 7.04 | 7.68 | 5.6 | 8.39 | 5.19
5.95 | 4.68 | 6.77 | 5.32 | 6.86 | 3.43 | 5.76 | 6.03 | 5.89 | 4.28
7.31 | 5.69 | 5.46 | 7.92 | 6.48 | 6.38 | 4.4 | 6.06 | 5.76 | 6.35
6.26 | 4.9 | 5.99 | 4.84 | 6.26 | 6.17 | 6.64 | 7.89 | 6.9 | 7.25
6.79 | 5.36 | 7.97 | 5.96 | 6.99 | 4.74 | 3.43 | 5.5 | 4.58 | 7.74
7.04 | 7.32 | 4.86 | 6.75 | 6.45 | 6.26 | 5.42 | 8.46 | 5.11 | 5.75
6.25 | 4.76 | 6.42 | 7.71 | 5.18 | 6.32 | 5.49 | 5.02 | 6.59 | 4.89
5.43 | 6.93 | 6.7 | 4.45 | 5.28 | 5.72 | 6.08 | 3.91 | 3.25 | 4.66
6.91 | 7.24 | 7.53 | 6.73 | 5.89 | 6.59 | 4.09 | 6.86 | 5.34 | 8.55
6.1 | 8.75 | 3.53 | 6.22 | 4.63 | 3.97 | 6.75 | 6.34 | 6 | 5.91
7.13 | 5.65 | 7.21 | 7.08 | 7.29 | 6.02 | 5.01 | 4.6 | 3.94 | 6.47
4.9 | 7.11 | 5.86 | 5.76 | 5.01 | 7.86 | 5.51 | 8.69 | 7.83 | 6.11
4.17 | 4.38 | 5.63 | 6.23 | 5.39 | 4.9 | 3.68 | 6.67 | 4.69 | 6.99
7.34 | 5.55 | 7.89 | 7.15 | 7.76 | 6.44 | 5.22 | 4.54 | 7.97 | 6.19
7.06 | 6.26 | 6.1 | 8.46 | 4.45 | 5.34 | 6.43 | 7.9 | 5.01 | 7.46
5.19 | 5.69 | 6.17 | 8.32 | 6.97 | 6.16 | 7.87 | 6.46 | 6.66 | 4.09
6.11 | 4.06 | 4.61 | 4.33 | 5.62 | 3.9 | 6.97 | 5.45 | 6.45 | 5.93
7.11 | 7.62 | 4.48 | 7.14 | 8.28 | 8.24 | 3.92 | 5.08 | 3.81 | 5.25
7.8 | 5.01 | 5.1 | 7.61 | 5.85 | 3.09 | 7.24 | 6.19 | 7.68 | 6.96
4.72 | 4.4 | 5.11 | 6.8 | 6.56 | 7.01 | 5.17 | 5.29 | 6.34 | 4.97
5.84 | 6.16 | 4.1 | 7.49 | 6.58 | 7.8 | 5.69 | 7.78 | 7.07 | 7
5.77 | 6.04 | 8.72 | 5.15 | 5.34 | 6.73 | 6.55 | 7.94 | 5.37 | 6.42
5.75 | 5.31 | 4.56 | 5.51 | 6.94 | 7.28 | 5.08 | 5.98 | 5.67 | 8.13
6.65 | 6.24 | 8.03 | 7.33 | 5.38 | 7.6 | 3.31 | 7.38 | 5.63 | 4.7
3.28 | 4.78 | 5.42 | 6.68 | 6.2 | 5.97 | 6.73 | 8.21 | 7.42 | 7.75
5.04 | 6.05 | 7.15 | 7.39 | 5.17 | 5.95 | 6.69 | 4.22 | 5.98 | 6.33
6.95 | 5.71 | 6.34 | 6.25 | 7.12 | 5.76 | 4.72 | 5.56 | 7.33 | 4.9
7.83 | 5.14 | 5.38 | 6.46 | 5.87 | 7.33 | 7.77 | 6.56 | 5.6 | 4.76
5.81 | 6.2 | 7.25 | 5.37 | 6.49 | 5.03 | 7.09 | 4.3 | 4.85 | 7.93
4.73 | 7.77 | 7.53 | 7.69 | 6.39 | 5.72 | 4.42 | 4.32 | 7.15 | 3.21
6.66 | 4.77 | 6.9 | 6.46 | 5.87 | 4.04 | 6.05 | 8.75 | 5.62 | 5.46
5.93 | 7.75 | 5.93 | 6.4 | 6.24 | 7.64 | 6.05 | 4.87 | 7.42 | 7.34
5.15 | 6.19 | 8.57 | 4.85 | 7.23 | 6.08 | 5.84 | 6.77 | 5.89 | 7.14
4.75 | 6.06 | 3.96 | 8.69 | 4.15 | 5.8 | 4.76 | 7.14 | 5.73 | 6.03
6.56 | 6.86 | 6.18 | 4.4 | 4.95 | 6.95 | 6.35 | 8.51 | 4.99 | 5.05
3.43 | 6.13 | 5.47 | 8.01 | 6.43 | 4.77 | 6.14 | 6.69 | 6.83 | 7.16
5.47 | 6.9 | 6.23 | 7.39 | 8.24 | 7.93 | 6.23 | 5.33 | 7.76 | 4.35
6.95 | 6.52 | 3.66 | 4.6 | 5.75 | 8.69 | 5.42 | 5.18 | 6.59 | 5.44
5.74 | 5.29 | 6.24 | 7.13 | 4.58 | 7.87 | 8.12 | 6.84 | 4.9 | 3.89
5.7 | 4.56 | 5.89 | 5.32 | 6.35 | 5.54 | 5.83 | 4.42 | 7.4 | 5.55
6.42 | 4.33 | 5.55 | 3.72 | 6.27 | 6.89 | 6.47 | 3.99 | 7.38 | 4.39
5.92 | 6.08 | 7.99 | 7.22 | 7.78 | 4.88 | 4.62 | 5.34 | 6.44 | 5.08
4.1 | 6.34 | 8.07 | 4.3 | 6.64 | 5.6 | 7.38 | 7.16 | 5.45 | 5.67
4.87 | 5.89 | 5.33 | 4.7 | 5.57 | 5.18 | 5.72 | 6.47 | 7.33 | 5.38
4.8 | 5.09 | 4.65 | 4.86 | 8.02 | 5.21 | 7.92 | 6.88 | 5.28 | 4.91
7.43 | 6.22 | 7.27 | 6.51 | 7.02 | 6.55 | 5.38 | 3.09 | 6.17 | 6.37
6.04 | 7.73 | 6.2 | 3.74 | 6.74 | 5.76 | 5.73 | 6.06 | 8.72 | 5.53
7.55 | 5.04 | 7.38 | 5.43 | 5.99 | 5.06 | 4.46 | 7.83 | 7.08 | 3.34
6.14 | 7.43 | 7.63 | 4.68 | 5.61 | 3.94 | 6.24 | 4.44 | 5.85 | 4.77
7.29 | 5.11 | 6.17 | 8.25 | 5.33 | 3.86 | 5.38 | 3.87 | 6.04 | 6.81
6.27 | 4.61 | 4.32 | 7.62 | 7.92 | 6.02 | 6.53 | 5.84 | 5.97 | 6.43
4.91 | 3.75 | 6.24 | 6.18 | 4.36 | 5.67 | 5.09 | 5.85 | 3.64 | 5.65
6.24 | 6.94 | 5.73 | 5.8 | 4.4 | 7.1 | 7.48 | 8.42 | 5.73 | 5.64
6.89 | 4.28 | 7.1 | 7.56 | 4.09 | 5.45 | 3.21 | 6.49 | 4.32 | 4.92
5.92 | 7.78 | 8.42 | 6.26 | 5.56 | 3.16 | 6.06 | 7.28 | 7.87 | 4.76
5.3 | 7.68 | 8.32 | 6.28 | 5.9 | 5.42 | 5.49 | 4.25 | 5.53 | 6.44
7.53 | 4.84 | 8.41 | 4.27 | 4.71 | 3.47 | 7.18 | 6.37 | 5.5 | 6.52
6.46 | 3.64 | 7.31 | 5.38 | 6.04 | 5.01 | 4.28 | 4.56 | 6.88 | 5.89
4.01 | 5.96 | 6.05 | 6.75 | 6.55 | 6.41 | 6.93 | 6.39 | 6.99 | 6.24
6.06 | 5.26 | 6.42 | 6.2 | 6.18 | 5.09 | 6.13 | 7.77 | 4.93 | 6.62
6.92 | 8.91 | 5.78 | 6.81 | 6.64 | 5.97 | 4.96 | 5.15 | 6.79 | 6.79
4.19 | 6.71 | 7.47 | 4.72 | 6.24 | 4.61 | 4.74 | 4.89 | 6.99 | 6.87
5.67 | 5.61 | 6.43 | 4.45 | 3.59 | 3.51 | 6.68 | 5.77 | 4.42 | 6.19
5.11 | 6.39 | 5.83 | 5.75 | 7.49 | 7.15 | 4.89 | 8.63 | 6.94 | 7.2
6.06 | 6.5 | 6.12 | 5.42 | 5.68 | 8.25 | 7.99 | 8.09 | 5.96 | 5.28
6.38 | 4 | 6.14 | 7.44 | 3.53 | 6.13 | 5.19 | 7.32 | 6.49 | 7.21
7.62 | 4.23 | 7.04 | 6.43 | 6.73 | 3.49 | 6.46 | 4.66 | 6.24 | 4.13
4.06 | 6.7 | 8.44 | 4.91 | 7.34 | 7.34 | 4.05 | 5.84 | 7.72 | 6.22
7.45 | 5.54 | 6.04 | 7.09 | 6.66 | 6.44 | 5.45 | 4.56 | 7.6 | 6.69
7.28 | 6.64 | 7.68 | 6.86 | 5.76 | 7.73 | 5.64 | 7.5 | 5.9 | 7.8
6.25 | 5.56 | 3.37 | 4.57 | 6.66 | 6.46 | 4.31 | 3.39 | 5.43 | 4.75
7.4 | 4.6 | 8.53 | 7.67 | 6.79 | 6.21 | 5.88 | 3.47 | 5.04 | 5.92
4.82 | 5.96 | 3.43 | 5.93 | 8.25 | 4.96 | 5.37 | 4.28 | 6.08 | 7.24
5.84 | 6.79 | 4.23 | 7.17 | 6.95 | 6.59 | 7.28 | 4.38 | 6.56 | 6.87
6.12 | 5.91 | 7.66 | 6.4 | 7.46 | 5.61 | 5.89 | 7.95 | 6.93 | 6.52
5.06 | 7.91 | 6.87 | 7.01 | 8.35 | 6.96 | 6.56 | 4.12 | 5.81 | 5.56
4.83 | 3.8 | 5.65 | 5.94 | 4.76 | 7.23 | 7.76 | 6.99 | 6.88 | 3.28
3.34 | 5.36 | 8.34 | 5.4 | 5.43 | 7.21 | 5.85 | 5.23 | 4.14 | 4.1
6.98 | 6.02 | 6.94 | 7.35 | 7.89 | 6.67 | 6.37 | 8.19 | 4.23 | 6.21
6.48 | 5.71 | 5.16 | 5.7 | 7.81 | 3.84 | 6.57 | 7.05 | 3.62 | 7.7
5.27 | 6.34 | 5.36 | 4.67 | 4.85 | 5.01 | 5.82 | 7.58 | 6.75 | 6.74
6.79 | 7.85 | 6.06 | 4.56 | 7.67 | 4.56 | 6.52 | 6.04 | 4.03 | 5.94
5.98 | 7.39 | 4.52 | 6.5 | 6.32 | 5.84 | 4.79 | 4.94 | 4.56 | 3.87
6.38 | 4.58 | 5.07 | 7.01 | 5.71 | 6.41 | 6.2 | 5.89 | 5.92 | 5.63
6.19 | 6 | 7.4 | 6.42 | 4.12 | 4.44 | 5.1 | 5.42 | 6.32 | 4.89
7.94 | 6.96 | 5.06 | 4.9 | 5.15 | 5.98 | 7.35 | 6.81 | 4.05 | 7.23
6.33 | 4.55 | 5.69 | 5.46 | 6.7 | 7.72 | 8.11 | 4.67 | 4.9 | 4.89
8.91 | 5.54 | 7.44 | 4.46 | 7.49 | 8.22 | 4.78 | 5.86 | 4.94 | 5.53
5.9 | 7.36 | 4.43 | 5.97 | 6.27 | 5.95 | 7.31 | 5.83 | 7.91 | 7.44
4.38 | 6.51 | 5.76 | 4.51 | 4.88 | 8.08 | 3.76 | 8.35 | 4.26 | 5.38
6.84 | 4.31 | 6.69 | 5.28 | 7.68 | 4.27 | 6.11 | 6.54 | 8.49 | 5.08
6.47 | 6.55 | 7.27 | 7.08 | 4.96 | 4.2 | 6.66 | 8.22 | 7.23 | 7.22
5.99 | 5.53 | 4.7 | 6.45 | 4.34 | 6.48 | 7.72 | 4.24 | 4.34 | 5.81
5.61 | 6.15 | 8.2 | 6.16 | 4.83 | 8.34 | 7.57 | 7.13 | 5.91 | 4.88
6.19 | 7.46 | 6.36 | 5.07 | 5.93 | 7.22 | 6.15 | 7.25 | 5.49 | 6.48
5.07 | 6.49 | 7.76 | 5.21 | 7.98 | 6.7 | 4.67 | 7.96 | 6.98 | 5.93
6.81 | 5.84 | 6.41 | 4.91 | 5.57 | 6.01 | 5.34 | 6.21 | 5.3 | 7.86
4.86 | 3.62 | 6.16 | 4 | 6.34 | 6.22 | 6.45 | 6.51 | 7 | 5.66
5.5 | 6.45 | 4.84 | 4.77 | 8.3 | 5.5 | 3.69 | 6.18 | 6 | 5.61
4.53 | 7.49 | 5.15 | 5.45 | 5.83 | 6.88 | 5.76 | 5.56 | 4.79 | 8.72
6.23 | 4.67 | 6.6 | 5.78 | 6.5 | 6.59 | 5.28 | 6.33 | 6.62 | 6.89
6.2 | 6.47 | 7.55 | 6.56 | 6.74 | 7.12 | 5.94 | 6.09 | 4.56 | 6.38
6.01 | 6.22 | 7.83 | 7.25 | 5.98 | 3.75 | 5.25 | 6.17 | 6.82 | 6.23
8.07 | 4.08 | 7.56 | 7.27 | 4.62 | 5.89 | 5.76 | 5.64 | 7.11 | 6.34
5.13 | 5.56 | 5.48 | 6.99 | 8.04 | 6.69 | 5.01 | 3.75 | 7.6 | 5.33
7.01 | 4.45 | 6.11 | 3.61 | 8.27 | 6.55 | 6.84 | 6.88 | 5.44 | 6.37
6.85 | 5.38 | 7.78 | 5.36 | 5.13 | 6 | 7.67 | 6.69 | 7.78 | 8.69
4.46 | 4.45 | 7.04 | 7.78 | 8.79 | 7.11 | 7.1 | 8.41 | 4.2 | 5.34
5.78 | 4.85 | 6.9 | 5.11 | 7.05 | 5.71 | 6.76 | 6.82 | 8.05 | 4.61
6.09 | 6.1 | 7.98 | 6.62 | 6.81 | 5.7 | 6.91 | 6.62 | 3.66 | 7.47
6.35 | 5.57 | 5.01 | 3.87 | 5.28 | 4.02 | 4.78 | 8.28 | 6.46 | 4.63
7.6 | 6.09 | 3.99 | 7.43 | 7.27 | 8.05 | 4.36 | 6.8 | 5.78 | 5.92
6.24 | 8.21 | 8.31 | 6 | 4.2 | 5.32 | 4.83 | 5.92 | 4.95 | 4.64
4.52 | 7.83 | 6.4 | 6.32 | 7.3 | 7.92 | 6.02 | 6.34 | 6.4 | 6.59
7.18 | 4.39 | 4.23 | 6.13 | 7.94 | 8.32 | 6.13 | 5.06 | 7.1 | 6.97
6.11 | 5.75 | 5.93 | 6.02 | 7.33 | 7.77 | 6.72 | 5.27 | 6.64 | 5.61
3.64 | 6.67 | 7.73 | 6.82 | 5.82 | 3.25 | 5.97 | 7.09 | 6.61 | 3.94
7.97 | 4.2 | 4.18 | 7.83 | 7.5 | 6.79 | 7.18 | 7.1 | 6.38 | 7.26
6.41 | 3.66 | 6.13 | 6.53 | 7.35 | 7.19 | 5.49 | 4.82 | 5.99 | 8.84
5.71 | 3.47 | 4.64 | 5.39 | 3.7 | 4.21 | 6.88 | 5.86 | 7.75 | 4.72
3.83 | 8.14 | 6.65 | 5.12 | 4.54 | 4.68 | 4.34 | 4.97 | 4.63 | 4.05
7.84 | 4.4 | 4.13 | 6.74 | 6.16 | 5.88 | 6.49 | 4.98 | 4.88 | 5.14
4.15 | 5.07 | 5.64 | 5.05 | 5.21 | 4.4 | 5.87 | 4.63 | 3.45 | 7.07
6.77 | 3.91 | 5.9 | 5.67 | 6.68 | 5.33 | 5.94 | 6.16 | 7.69 | 7.07
3.93 | 4.38 | 4.77 | 5.63 | 6.61 | 6.52 | 5.8 | 8.04 | 7.44 | 5.49
5.54 | 4.25 | 4.46 | 4.14 | 6.5 | 5.86 | 6.78 | 4.78 | 5.94 | 7.65
5.74 | 5.32 | 6.93 | 4.79 | 6.45 | 7.31 | 5.7 | 6.83 | 6.74 | 7.85
6.63 | 3.28 | 3.85 | 5.41 | 4.17 | 7.19 | 6 | 4.43 | 5.63 | 4.56
6.12 | 4.35 | 7.85 | 6.04 | 3.45 | 4.52 | 7.3 | 5.53 | 3.72 | 7.18
4.32 | 5.15 | 6.58 | 7.79 | 7.14 | 6.04 | 6.35 | 7.02 | 6.12 | 4.03
5.65 | 4.67 | 5.72 | 6.76 | 4.64 | 6.85 | 7.33 | 8.26 | 6.19 | 7.61
5.82 | 7.6 | 7.44 | 4.63 | 6 | 6.27 | 5.8 | 5.38 | 4.83 | 3.25
5.65 | 6.44 | 5.4 | 5.04 | 7.3 | 5.84 | 5.68 | 5.57 | 5.96 | 7.16
6.45 | 3.65 | 6.91 | 4.15 | 5.95 | 8 | 4.35 | 7.8 | 7.52 | 3.66
5.4 | 6.85 | 6.08 | 6.98 | 6.75 | 7.25 | 3.51 | 5.39 | 4.25 | 4.02
4.13 | 3.58 | 6.69 | 4.83 | 5.62 | 5.37 | 5.46 | 5.93 | 6.49 | 6.93
5.72 | 5.3 | 6.68 | 3.81 | 4.67 | 6.47 | 5.02 | 4.37 | 6.26 | 4.7
6.21 | 5.74 | 5.27 | 5.54 | 3.9 | 5.54 | 4.3 | 5.44 | 4.67 | 3.76
5.97 | 6.78 | 8.04 | 5.11 | 3.54 | 7.18 | 5.39 | 3.8 | 7.64 | 5.88
5.37 | 5.44 | 6.71 | 4.32 | 6 | 7.64 | 6.12 | 5.55 | 5.44 | 7.15
6.13 | 5.66 | 5.23 | 7.12 | 5.45 | 6.08 | 5.6 | 5.78 | 6.48 | 3.49
4.66 | 6.28 | 7.86 | 4.36 | 5.51 | 4.24 | 5.41 | 5.72 | 4.8 | 5.11
3.86 | 4.63 | 6.86 | 5.83 | 6.52 | 6.28 | 5.06 | 5.62 | 5.27 | 6.33
5.8 | 7.17 | 5.58 | 6.19 | 5.9 | 4.05 | 5.67 | 5.81 | 6.93 | 8.31
6.5 | 7.27 | 4.85 | 7.99 | 5.72 | 5.22 | 6.2 | 6.69 | 5.62 | 5.68
6.15 | 7.12 | 5.38 | 6.24 | 6.79 | 7.47 | 6.69 | 6.67 | 7.67 | 5.13
6.01 | 4.96 | 8 | 4.87 | 4.55 | 5.51 | 7.42 | 5.97 | 4.98 | 5.69
5.12 | 6.08 | 5.18 | 3.41 | 8.14 | 4.17 | 5.77 | 5.67 | 6.6 | 8.36
4.41 | 4.81 | 7.22 | 6.81 | 6.05 | 7.48 | 4.49 | 7.67 | 5.98 | 6.67
4.51 | 6.75 | 4.94 | 6.61 | 5.81 | 5.36 | 6.56 | 6.78 | 6.39 | 6.73
5.44 | 5.4 | 7.8 | 5.37 | 6.22 | 6.57 | 5.29 | 4.69 | 6.11 | 6.27
4.57 | 8.04 | 4.95 | 7.15 | 5.1 | 4.82 | 5.44 | 5.42 | 7.39 | 7.42
4.65 | 7.33 | 4.79 | 4.17 | 6.1 | 8.07 | 6.83 | 6.95 | 7.04 | 5.48
5.56 | 5.46 | 6.73 | 8.18 | 5.94 | 7.24 | 7.45 | 4.8 | 5.99 | 5.71
4.81 | 6.58 | 6 | 5.53 | 4.47 | 6.43 | 5.21 | 7.61 | 5.21 | 4.3
5.98 | 5.72 | 8.91 | 6.12 | 4.13 | 4.78 | 7.26 | 5.13 | 4.68 | 7.11
4.94 | 7.67 | 5.63 | 7.88 | 4.75 | 3.41 | 5.61 | 6.79 | 5.25 | 5.13
4.59 | 5.62 | 6.61 | 7.32 | 5.58 | 4.66 | 5.54 | 6.23 | 6.23 | 6.45
7.1 | 7.59 | 5.77 | 8.08 | 3.65 | 5.22 | 7.32 | 4.03 | 6.25 | 7.27
4.62 | 5.03 | 5.05 | 6.47 | 4.33 | 5.31 | 4.91 | 5.95 | 5.43 | 5.01
4.09 | 3.16 | 4.3 | 5.19 | 7.86 | 6.48 | 5.02 | 7.77 | 6.86 | 6.79
4.69 | 7.5 | 6.45 | 5.33 | 5.86 | 5.73 | 5.82 | 5.05 | 5.31 | 6.82
5.58 | 5.97 | 7.62 | 6.41 | 6.76 | 5.58 | 6.96 | 5.33 | 6.59 | 5.21
5.96 | 5.93 | 5.17 | 6.64 | 5.83 | 6.04 | 5.26 | 4.48 | 7.7 | 5.11
5.82 | 5.32 | 5.37 | 7.21 | 3.85 | 7.55 | 5.75 | 6.46 | 7.64 | 7.96
6.53 | 5.87 | 7.57 | 6 | 5.51 | 5.73 | 7.26 | 5.04 | 7.73 | 5.77
7.56 | 7.71 | 6.71 | 7.54 | 5.81 | 5.46 | 5.85 | 5.58 | 3.74 | 4.79
6.38 | 5.38 | 8.12 | 5.72 | 5.88 | 4.34 | 7.19 | 7.8 | 5.68 | 8.63
5.16 | 6.27 | 8.27 | 4.01 | 4.25 | 8.17 | 7.4 | 5.74 | 5.56 | 6.34
6.2 | 5.14 | 6.34 | 5.29 | 7.28 | 5.05 | 4.58 | 5.57 | 4.71 | 8.46
3.79 | 6.15 | 5.82 | 4.68 | 6.19 | 4.58 | 5.73 | 7.42 | 4.57 | 8.34
4.94 | 7.4 | 7.61 | 4.75 | 6.37 | 6.21 | 5.53 | 5.09 | 7.05 | 5.12
5.83 | 7.28 | 4.09 | 6.69 | 5.53 | 7.6 | 3.89 | 6.68 | 5.26 | 3.93
8.15 | 7.56 | 4.5 | 8.63 | 5.73 | 7.83 | 6.73 | 8.14 | 7.62 | 4.82
6.77 | 6.17 | 7.95 | 4.52 | 8.69 | 5.88 | 6 | 6.61 | 4.78 | 8.42
6.54 | 3.88 | 5.67 | 6.03 | 5.02 | 7.42 | 3.47 | 4.89 | 4.18 | 6.1
5.64 | 6.38 | 5.2 | 6.35 | 7.34 | 4.71 | 5.41 | 5.99 | 4.84 | 6.14
8.51 | 3.89 | 5.29 | 5.06 | 7.53 | 5.94 | 5.55 | 7.57 | 6.03 | 4.68
5.62 | 6.83 | 5.08 | 5.58 | 4.83 | 6.02 | 3.9 | 6.78 | 4.09 | 5.87
8.66 | 3.86 | 5.61 | 8 | 5.65 | 7.39 | 5.62 | 6.66 | 5.07 | 5.81
7.23 | 5.77 | 5.36 | 8.11 | 4.04 | 4.61 | 7.2 | 4.23 | 5.64 | 5.87
4.53 | 8.22 | 7.81 | 7.07 | 4.61 | 7.4 | 7.78 | 5.13 | 6.02 | 5.42
6.76 | 6.77 | 6.14 | 4.03 | 7.6 | 7.1 | 7.23 | 5.58 | 5.72 | 6.05
5.05 | 4.41 | 7.6 | 5.65 | 5.99 | 6.17 | 5.5 | 6.11 | 6.47 | 7.63
4.35 | 4.87 | 7.03 | 3.8 | 7.03 | 7.05 | 5.61 | 5.44 | 6.94 | 5.14
5.7 | 3.85 | 7.96 | 3.85 | 4.69 | 5.01 | 8.1 | 3.62 | 5.79 | 6.19
7.32 | 6.41 | 8.66 | 5.89 | 6.96 | 6.05 | 6.73 | 4.83 | 4.63 | 7.17
6.92 | 5.48 | 4.82 | 5.68 | 7.68 | 5.92 | 6.64 | 5.46 | 5.74 | 5.75
4.43 | 4.58 | 6.75 | 6.01 | 6.62 | 5.79 | 8.91 | 6.96 | 7.3 | 4.9
4.21 | 6 | 5.7 | 5.39 | 5.83 | 6.87 | 7.14 | 5.36 | 4.44 | 5.95
6.72 | 6 | 5.46 | 4.99 | 5.67 | 4.96 | 5.91 | 6.5 | 7.17 | 5.55
6.93 | 6.11 | 4.12 | 5.54 | 5.87 | 8.31 | 4.66 | 5.94 | 4.13 | 6.63
5.68 | 6.37 | 7.49 | 7.05 | 5.85 | 6.78 | 4.93 | 5.27 | 5.58 | 5.02
5.88 | 4.51 | 4.95 | 8.59 | 6.22 | 4.46 | 5.95 | 7.62 | 8.17 | 7.01
8.79 | 3.99 | 5.21 | 6.02 | 5.06 | 6.09 | 6.27 | 7.87 | 7.2 | 6.58
5.27 | 4.53 | 6.76 | 7.26 | 7.48 | 6.14 | 6.54 | 5.54 | 5.15 | 6.93
3.96 | 7.86 | 4.54 | 7.65 | 6.42 | 6 | 8.79 | 6.4 | 3.87 | 4.45
6.25 | 6.23 | 5.74 | 5.1 | 6.13 | 5.12 | 4.81 | 5.6 | 6.52 | 6.06
6.57 | 4.09 | 6.2 | 5.69 | 5.71 | 4.57 | 5.52 | 5.56 | 6.86 | 6.27
5.86 | 6.14 | 5.01 | 7.16 | 8.18 | 5.2 | 6.71 | 5.79 | 6.66 | 5.56
8.49 | 3.73 | 5.05 | 7.12 | 6.69 | 5.91 | 7.14 | 7.82 | 4.27 | 7.12
4.02 | 7.98 | 4.75 | 5.17 | 5.01 | 7.21 | 8.05 | 6.52 | 6.32 | 5.01
6.32 | 4.46 | 6.02 | 4.78 | 6.24 | 7.46 | 4.98 | 6.63 | 4.55 | 7.5
4.74 | 6.72 | 7.07 | 6.65 | 6.81 | 6 | 7.6 | 3.86 | 7.07 | 6.37
6.09 | 6.63 | 5.01 | 6.06 | 4.65 | 4.7 | 6.44 | 5.46 | 6.55 | 4.99
6.51 | 5.72 | 6.61 | 7.4 | 7.15 | 5.55 | 6.87 | 7.51 | 3.28 | 4.53
5.55 | 6.1 | 6.64 | 6.98 | 5.63 | 7.58 | 7.43 | 7.4 | 6.81 | 6.08
4.25 | 6.63 | 6.54 | 4.49 | 6.51 | 7.47 | 6.57 | 5.59 | 4.3 | 3.72
4.71 | 5.65 | 6.21 | 6.19 | 3.61 | 6.01 | 6.21 | 4.02 | 5.67 | 3.09
3.76 | 4.97 | 5.54 | 6.09 | 3.76 | 6.72 | 6.61 | 5.83 | 7.04 | 7.99
5.9 | 6.05 | 5.77 | 5.54 | 4.93 | 4.89 | 5.35 | 6.28 | 6.25 | 7.82
8.59 | 5.8 | 6.47 | 7.73 | 7.22 | 5.07 | 5.96 | 5.9 | 3.7 | 3.56
4.12 | 7.58 | 3.83 | 5.93 | 6.26 | 5.5 | 5.07 | 4.01 | 4.25 | 5.67
7.48 | 5.81 | 5.89 | 6.58 | 6.54 | 5.08 | 6.05 | 6.71 | 4.06 | 4.67
4.5 | 5.22 | 6.96 | 5.64 | 4.91 | 6 | 5.81 | 5.7 | 5.35 | 5.74
7.04 | 5.3 | 4.45 | 7.18 | 4.18 | 7.71 | 6.17 | 4.41 | 7.61 | 3.85
7 | 6.64 | 5.66 | 7.1 | 3.75 | 5.52 | 5.46 | 5.38 | 4.44 | 5.71
7.87 | 5.54 | 7.18 | 3.31 | 6.69 | 5.16 | 5.96 | 7.49 | 6.92 | 5.88
5.53 | 6.66 | 8.17 | 5.45 | 5.59 | 3.93 | 5.58 | 6.59 | 7 | 4.42
7.08 | 5.27 | 5.74 | 8.34 | 6.19 | 5.45 | 6.75 | 6.76 | 6.05 | 7.11
5.39 | 5.76 | 7.33 | 5.97 | 7.2 | 8.75 | 7.46 | 8.07 | 7.86 | 6.43
5.99 | 7.99 | 7.34 | 5.01 | 7.04 | 7.39 | 7.56 | 6.43 | 5.17 | 5.04
5.52 | 6.24 | 4.66 | 6.03 | 5.3 | 5.54 | 7.39 | 6.58 | 6.11 | 5.19
4.79 | 7.56 | 5.22 | 7.46 | 5.89 | 6.13 | 4.8 | 8.59 | 7.03 | 7.14
6.34 | 4.47 | 7.56 | 4.04 | 4.7 | 7.81 | 7.07 | 6.38 | 7.47 | 4.65
6.5 | 5.95 | 5.56 | 7.37 | 7.27 | 4.3 | 6.87 | 6.48 | 7.31 | 6.56
6.61 | 6.91 | 6.89 | 7.02 | 6.21 | 6.54 | 6.24 | 7.91 | 5.14 | 6.77
5.88 | 4.74 | 4.63 | 5.29 | 6.49 | 7.96 | 4.43 | 4.36 | 4.48 | 5.58
6.6 | 6.81 | 6.81 | 6.27 | 4.75 | 5.55 | 4.84 | 7.49 | 4.81 | 3.54
6.68 | 5.72 | 5.34 | 6.49 | 5.96 | 5.23 | 6.48 | 5.84 | 7.8 | 4.57
8.11 | 6.62 | 7.42 | 3.86 | 6.38 | 6.83 | 5.47 | 6.05 | 8.84 | 6.35
7.37 | 5.84 | 6.18 | 5.35 | 5.55 | 5.82 | 5.78 | 4.6 | 5.39 | 7.04
6.65 | 7.22 | 4.91 | 3.21 | 4.8 | 5.97 | 6.48 | 4.81 | 6.57 | 6.15
5.18 | 7.87 | 6.8 | 4.93 | 6.88 | 4.28 | 7.89 | 6.66 | 6.48 | 4.85
7.16 | 8.05 | 7.42 | 8.14 | 7.38 | 5.96 | 7.55 | 4.58 | 6.41 | 8.03
5.87 | 7.37 | 7.65 | 4.96 | 4.9 | 6.28 | 7.37 | 5.62 | 6.35 | 4.91
5.54 | 4.8 | 3.91 | 5.5 | 5.58 | 6.86 | 8.15 | 4.38 | 7.5 | 4.43
3.45 | 4.9 | 4.96 | 6.47 | 6.22 | 4.43 | 6.41 | 7.39 | 5.34 | 5.35
5.45 | 7.1 | 4.88 | 4.09 | 8.15 | 5.08 | 8.06 | 4.42 | 6.57 | 5.77
4.08 | 7.6 | 7.46 | 5.08 | 4.23 | 7.04 | 7.2 | 6.27 | 5.95 | 6.47
5.06 | 7.68 | 5.38 | 7.27 | 4.22 | 5.77 | 7.35 | 7.08 | 5.4 | 7.33
6.7 | 7.55 | 4.51 | 6.86 | 6.59 | 5.05 | 5.77 | 6.94 | 5.52 | 7.84
5.32 | 5.98 | 6.7 | 6.08 | 7.37 | 6.73 | 6.19 | 5.66 | 5.08 | 7.79
7.89 | 6.03 | 8.25 | 4.82 | 4.92 | 8.66 | 4.02 | 4.09 | 5.89 | 4.23
5.65 | 6.62 | 4.08 | 5.5 | 5.22 | 6.24 | 6.72 | 8.72 | 5.87 | 5.72
7.05 | 3.72 | 7.87 | 4.56 | 8.72 | 6.61 | 7.02 | 5.54 | 5.21 | 6.88
8.24 | 5.97 | 5.61 | 8.84 | 4.24 | 4.47 | 8.3 | 6.13 | 6.36 | 4.61
6.37 | 6.18 | 3.16 | 3.9 | 6.06 | 7.55 | 6.06 | 6.17 | 4.87 | 8.24
5.46 | 7.97 | 5.96 | 5.9 | 5.62 | 6.32 | 7.7 | 5.36 | 6.19 | 5.26
7.62 | 7.97 | 6.78 | 6.48 | 5.66 | 3.61 | 4.84 | 6.09 | 7.19 | 7.39
5.79 | 6.2 | 4.38 | 5.6 | 5.36 | 7.69 | 8.31 | 7.52 | 7.25 | 8.11
4.47 | 7.04 | 5.86 | 4.89 | 5.95 | 5.44 | 4.39 | 7 | 4 | 3.41
7.95 | 5.7 | 5.68 | 5.53 | 5.44 | 6.1 | 6.23 | 8.39 | 5.78 | 6.38
4.79 | 8.38 | 7.72 | 5.16 | 5.39 | 4.06 | 5.93 | 3.53 | 6.41 | 7.11
6.94 | 5.37 | 5.65 | 6.18 | 6.93 | 6.69 | 6.17 | 3.82 | 4.73 | 7.88
6.82 | 6.25 | 7.43 | 5.14 | 5.04 | 7.24 | 5.04 | 5.06 | 5.75 | 5.35
7.1 | 5.2 | 6.88 | 4.54 | 6.79 | 4.51 | 5.9 | 7.22 | 5.82 | 6.06
5.83 | 5.86 | 7.39 | 8.91 | 5.24 | 7.29 | 6.48 | 6.89 | 7.22 | 3.62
5.83 | 7.49 | 4.39 | 4.19 | 7.25 | 6.12 | 5.11 | 5.37 | 7.36 | 5.11
4.99 | 7.76 | 5.45 | 5.1 | 4.53 | 6.52 | 6.28 | 5.69 | 5.75 | 6.67
6.41 | 6.19 | 6.99 | 5.56 | 7.33 | 7.01 | 4.08 | 8.05 | 7.02 | 7.54
3.68 | 5.53 | 7.06 | 8.31 | 7.03 | 6.61 | 6.79 | 6.52 | 5.5 | 6.83
7.12 | 7.37 | 4.27 | 4.21 | 4.82 | 5.76 | 6.89 | 5.03 | 6.63 | 6.02
4.84 | 6.28 | 4.38 | 7.77 | 6.77 | 5.65 | 4.48 | 5.76 | 5.71 | 6.92
6.48 | 5.94 | 5.04 | 6.19 | 4.51 | 7.9 | 5.01 | 4.25 | 5.93 | 7.56
6.82 | 5.19 | 3.58 | 6.27 | 6.6 | 4.31 | 6.86 | 4.03 | 6.5 | 3.39
7.85 | 4.32 | 6.28 | 6.64 | 5.11 | 4.25 | 7.83 | 6.81 | 6.58 | 4.14
4.93 | 6.73 | 7.91 | 5.87 | 5.09 | 4.01 | 3.84 | 6.22 | 6.14 | 6.2
5.81 | 6.42 | 5.64 | 6.95 | 6.72 | 7.14 | 5.86 | 5.08 | 7.96 | 5.01
6.56 | 8.44 | 5.02 | 7.25 | 5.92 | 7.38 | 6.54 | 6.42 | 6.92 | 7.13
5.91 | 5.39 | 6.46 | 4.57 | 5.08 | 4.69 | 5.79 | 7.28 | 6.37 | 3.58
6.07 | 6.6 | 7.5 | 7.55 | 7.72 | 4.51 | 6.53 | 6.66 | 3.92 | 7.55
3.25 | 5.08 | 4.44 | 6.66 | 5.29 | 6.08 | 6.28 | 6.93 | 5.73 | 6.02
6.56 | 6.47 | 6.46 | 5.44 | 5.42 | 7.8 | 6.62 | 4.86 | 4.61 | 4.6
4.3 | 5.87 | 4.98 | 7.95 | 7.4 | 6.38 | 6.51 | 6.99 | 5.65 | 6.75
6.78 | 4.69 | 7.91 | 5.02 | 4.97 | 5.62 | 6.41 | 7.29 | 6.13 | 7.6
6.86 | 8.03 | 7.87 | 6.14 | 5.49 | 4.77 | 7.03 | 5.64 | 4.67 | 8.18
6.78 | 7.8 | 3.62 | 7.6 | 4.26 | 8.72 | 6.98 | 8.32 | 8.22 | 5.41
4.29 | 4.03 | 6.89 | 5.65 | 5.1 | 3.72 | 7.64 | 5.89 | 6.7 | 5.66
7.5 | 7.26 | 3.73 | 5.95 | 5.69 | 5.81 | 7.44 | 5.85 | 6.22 | 5.38
6.57 | 6.43 | 5.27 | 6.15 | 6.03 | 6.82 | 5.51 | 8.57 | 6.62 | 5.44
8.69 | 4.05 | 6.49 | 4.96 | 6.23 | 6.4 | 7.91 | 7.31 | 7.66 | 5.27
6.75 | 6.35 | 6.2 | 6.39 | 5.66 | 5.78 | 5.79 | 6.15 | 5.88 | 4.77
3.85 | 5.39 | 6.54 | 8.27 | 7.41 | 4.99 | 5.23 | 5.35 | 5.29 | 6.67
5.18 | 6.71 | 5.67 | 5.27 | 6.35 | 6.74 | 5.7 | 6.68 | 8.44 | 3.74
4.89 | 5.36 | 6.23 | 7.68 | 5.7 | 6.62 | 6.18 | 8.2 | 5.34 | 6.7
5.2 | 5.03 | 5.61 | 4.66 | 7.56 | 6.27 | 4.45 | 7.09 | 6.52 | 5.58
8.04 | 6.48 | 6.33 | 5.02 | 6.46 | 6.24 | 5.65 | 7.71 | 6.35 | 4.67
5.63 | 5.39 | 7.05 | 4.34 | 5.91 | 8.61 | 3.91 | 8.15 | 3.53 | 4.16
7.27 | 4.85 | 3.7 | 6.84 | 7.42 | 5.58 | 6.92 | 5.46 | 8.38 | 3.37
4.13 | 7.39 | 7.15 | 7.87 | 6.95 | 6.05 | 8.19 | 4.72 | 6.09 | 4.25
6.12 | 4.57 | 8.36 | 7.11 | 4.38 | 7.52 | 4.4 | 6.22 | 6.9 | 5.2
5.37 | 6.76 | 4.76 | 8.38 | 4.5 | 6.39 | 4.95 | 6.38 | 6.2 | 5.9
3.65 | 4.88 | 7.3 | 6.61 | 6.48 | 5.34 | 4.06 | 6.04 | 8.06 | 6.24
4.16 | 7.46 | 5.34 | 6.84 | 5.48 | 5.1 | 4.5 | 8.13 | 5.02 | 4.22
5.62 | 5.42 | 4.35 | 6.24 | 6.61 | 5.57 | 5.89 | 6.1 | 5.41 | 5.5
3.37 | 8.46 | 7.3 | 4.36 | 4.31 | 7.25 | 5.46 | 6.21 | 5.18 | 8.28
5.46 | 5.08 | 5.22 | 6.6 | 7.32 | 6.03 | 5.64 | 4.96 | 6.13 | 5.96
4.65 | 6.4 | 5.68 | 8.12 | 6.4 | 5.27 | 5.23 | 3.74 | 5.68 | 6.78
4.39 | 6.59 | 8.24 | 5.27 | 7.25 | 7.37 | 6.4 | 6.23 | 6.85 | 7.05
7.43 | 5.76 | 3.81 | 6.95 | 4.16 | 3.98 | 6.02 | 5.76 | 6.26 | 5.89
3.74 | 5.57 | 4.42 | 6.04 | 6.83 | 4.45 | 4.61 | 4.53 | 5.38 | 3.81
6.97 | 5.73 | 6.22 | 3.43 | 5.6 | 7.76 | 4.68 | 7.53 | 5.93 | 5.97
7.54 | 4.53 | 6.78 | 5.03 | 6.1 | 5.48 | 5.5 | 5.66 | 4.13 | 3.88
5.5 | 4.18 | 6.95 | 7.97 | 5.78 | 3.7 | 8.07 | 6.91 | 8.16 | 5.57
5.62 | 4.89 | 7.02 | 5.64 | 5.54 | 5.83 | 4.63 | 7.75 | 5.06 | 5.43
8.2 | 5.17 | 3.65 | 5.87 | 4.56 | 5.1 | 5.52 | 6.27 | 5.81 | 5.52
5.33 | 8.79 | 4.31 | 5.59 | 7.07 | 3.66 | 3.73 | 6.62 | 7.21 | 4.13
4.17 | 6.88 | 7.39 | 7.83 | 6.26 | 6.53 | 7.87 | 5.21 | 6.51 | 7.08
6.69 | 8.72 | 5.85 | 6.5 | 8.01 | 5.94 | 5.89 | 3.84 | 4.23 | 5.12
6.75 | 5.83 | 4 | 6.52 | 5.01 | 4.89 | 3.78 | 5.65 | 7.39 | 6.08
6.28 | 6.54 | 3.28 | 6.24 | 6.61 | 7.54 | 6.1 | 4.99 | 6.55 | 6.69
3.92 | 6.45 | 5.82 | 3.84 | 6.63 | 5.77 | 6.08 | 6.1 | 6.74 | 7.08
7.52 | 6.14 | 7.71 | 7.19 | 6.62 | 6.49 | 4.69 | 5.91 | 5.85 | 6.85
5.9 | 6.8 | 7.18 | 7.97 | 7.85 | 7.91 | 6.35 | 7.56 | 4.61 | 5.68
6.05 | 5.31 | 7.6 | 5.89 | 4.8 | 4.48 | 7.11 | 4.63 | 7.21 | 7.27
4.89 | 6.73 | 6.83 | 7.1 | 5.48 | 5.58 | 5.34 | 3.69 | 6.66 | 4.53
5.54 | 7.38 | 6.74 | 5.49 | 3.58 | 4.62 | 3.98 | 3.21 | 5 | 6.59
7.38 | 6.4 | 4.05 | 4.67 | 5.31 | 5.93 | 6.32 | 4.51 | 7.65 | 5.59
6.26 | 4.71 | 5.89 | 6.6 | 6.4 | 5.56 | 5.71 | 6.35 | 5.53 | 5.48
5.57 | 5.59 | 4.76 | 7.91 | 4.28 | 6.98 | 4.82 | 6.83 | 5.24 | 5.16
5.44 | 7.33 | 5.73 | 5.62 | 4.54 | 7.98 | 4.42 | 6.9 | 6.53 | 5.49
6.99 | 5.33 | 6.98 | 4.77 | 4.44 | 5.78 | 3.93 | 6.28 | 5.42 | 5.27
5.11 | 7.19 | 4.62 | 6.13 | 3.97 | 6.83 | 6.61 | 6.89 | 5.39 | 4.87
7.61 | 8.51 | 6.02 | 6.78 | 6.51 | 3.95 | 7.82 | 6.18 | 4.37 | 4.48
7.21 | 6.89 | 4.36 | 6.87 | 7.7 | 7.09 | 6.14 | 4.18 | 3.73 | 8
4.54 | 5.86 | 5.47 | 4.06 | 6.35 | 7.44 | 7.27 | 4.82 | 6.45 | 7.89
5.97 | 4.5 | 4.03 | 4.48 | 6.89 | 6.11 | 5.1 | 5.42 | 5.5 | 6.55
5.44 | 5.05 | 4.6 | 3.91 | 8.06 | 5.87 | 7.79 | 5.18 | 4.73 | 7.28
7.77 | 3.39 | 5.79 | 3.34 | 4.29 | 5.68 | 7.31 | 5.92 | 6.71 | 5.94
6.99 | 5.52 | 7.43 | 4.79 | 6.11 | 3.74 | 4.91 | 4.4 | 6.13 | 4.99
4.2 | 6.13 | 3.76 | 5.69 | 6.55 | 6.08 | 5.83 | 8.55 | 6.64 | 7.58
5.21 | 3.96 | 5.87 | 5.73 | 6.66 | 4.08 | 7.23 | 6.58 | 5.51 | 5.91
4.68 | 5.77 | 4.59 | 5.93 | 7.39 | 4.38 | 5.97 | 7.68 | 4.1 | 4.06
6.07 | 6.86 | 5.08 | 6.09 | 5.55 | 6.23 | 3.95 | 5.41 | 7.71 | 8.44
4.97 | 4.79 | 7.66 | 4.86 | 6.99 | 6.99 | 6.88 | 5.7 | 8.42 | 7.87
5.03 | 5.19 | 6.72 | 5.71 | 5.63 | 5.38 | 6.04 | 5.82 | 7.18 | 8.35
5.27 | 7.15 | 4.88 | 8.75 | 6.07 | 4.03 | 7.75 | 7.64 | 3.98 | 7.22
7.7 | 6.79 | 5.19 | 6.63 | 6.15 | 7.59 | 3.65 | 5.3 | 5.83 | 5.79
6.13 | 7.07 | 5.83 | 5.98 | 3.73 | 6.34 | 7.53 | 4.23 | 5.72 | 5.7
5.76 | 7.91 | 3.75 | 6.73 | 6.12 | 7.72 | 7.25 | 6.2 | 6.83 | 6.4
7.07 | 5.34 | 6.84 | 5.82 | 7.64 | 5.64 | 5.7 | 5.87 | 4.83 | 7.4
5.08 | 6.56 | 7.29 | 6.14 | 8.07 | 5.86 | 4.65 | 7.81 | 6.14 | 8.17
7.02 | 3.51 | 5.25 | 7.36 | 4.13 | 8.02 | 7.5 | 6.01 | 5.08 | 6.99
6.83 | 6.36 | 5.57 | 7.24 | 5.7 | 4.73 | 5.72 | 5.37 | 6.43 | 5.18
6.13 | 4.34 | 5.88 | 5.38 | 5.35 | 8.04 | 8.38 | 5.74 | 4.21 | 6.6
7.33 | 7.81 | 3.41 | 7.2 | 7.04 | 6.46 | 6.99 | 6.35 | 7.11 | 7.48
6.86 | 4.61 | 4.5 | 3.73 | 4.02 | 4.47 | 5.93 | 5.28 | 6.24 | 4.41
5.19 | 3.92 | 4.39 | 5.09 | 6.82 | 6.74 | 7.86 | 6.16 | 7.98 | 4.47
5.15 | 3.09 | 6.62 | 7.04 | 6.77 | 4.13 | 4.16 | 7.44 | 5.99 | 3.96
7.3 | 5.09 | 4.29 | 3.56 | 4.86 | 7.43 | 4.52 | 5.94 | 7.46 | 5.62
5.83 | 3.25 | 6.82 | 5.81 | 5.46 | 6.89 | 5.84 | 6.27 | 4.75 | 6.79
6.05 | 6.76 | 6.55 | 4.53 | 8.08 | 4.92 | 4.54 | 3.85 | 7.97 | 3.92
6.39 | 6.58 | 7.52 | 4.42 | 5.88 | 6.05 | 6.42 | 4.1 | 5.23 | 5.6
6.89 | 7.29 | 6.96 | 6.18 | 6.03 | 5.94 | 5.85 | 4.75 | 5.45 | 6.42
7.81 | 6.99 | 4.63 | 4.69 | 6.15 | 3.68 | 5.4 | 5.63 | 6.76 | 5.24
8.14 | 5 | 7.13 | 8.47 | 8.36 | 5.97 | 6.09 | 7.97 | 5.54 | 5.73
6.73 | 5.5 | 6.25 | 7.64 | 5.96 | 7.68 | 6.46 | 4.96 | 5.61 | 5.98
4.67 | 4.24 | 6.55 | 5.85 | 6.56 | 8.27 | 4.95 | 6.45 | 6.38 | 6.14
5.25 | 7.44 | 8.38 | 5.99 | 6.08 | 5.69 | 4.99 | 4.95 | 5.98 | 7.43
5.6 | 6.97 | 6.56 | 8.2 | 4.43 | 6.19 | 5.25 | 4.93 | 7.49 | 8.32
5.17 | 6.46 | 3.89 | 5.62 | 8.09 | 5.21 | 5.56 | 3.51 | 6.72 | 4.19
5.85 | 5.93 | 5.65 | 5.92 | 6.12 | 7.13 | 7.3 | 7.63 | 5.25 | 4.63
7.46 | 7.52 | 7.14 | 5.26 | 7.24 | 4.87 | 3.34 | 7.3 | 6.23 | 4.8
5.33 | 5.96 | 8.11 | 6.44 | 4.5 | 5.41 | 4.2 | 4.83 | 5.03 | 6.17
5.52 | 6.75 | 8.51 | 7.16 | 6.47 | 4.69 | 7.12 | 6.64 | 5.87 | 6.18
8.34 | 6.16 | 6.84 | 4.23 | 5.03 | 7.18 | 7.28 | 7.16 | 5.69 | 6.15
4.96 | 8.32 | 7.4 | 6.1 | 8.11 | 6.12 | 8.04 | 5.4 | 4.64 | 6.51
5.38 | 7.22 | 5.12 | 3.59 | 5.18 | 5.61 | 4.18 | 4.87 | 6.27 | 6.95
5.43 | 4.97 | 6.12 | 5.14 | 4.69 | 5.52 | 7.43 | 7.45 | 7.01 | 5.07
5.41 | 5.58 | 5.82 | 7.84 | 7.13 | 6.47 | 7.8 | 5.07 | 6.04 | 6.75
3.16 | 5.04 | 4.26 | 6.75 | 6.59 | 5.79 | 5.17 | 5.25 | 6 | 7.64
3.58 | 3.31 | 6.21 | 7.42 | 8.05 | 6.33 | 7.25 | 7.27 | 4.81 | 5.25
4.61 | 7.92 | 5.62 | 5.15 | 6.85 | 5.91 | 6.94 | 4.05 | 7.68 | 6.17
4.63 | 4.66 | 6.4 | 5.45 | 6.16 | 6.12 | 5.4 | 6.22 | 5.96 | 7.05
5.97 | 6.02 | 6.32 | 7.58 | 5.67 | 5.9 | 5.24 | 5.68 | 5.63 | 8.66
7.68 | 3.43 | 6.52 | 6.08 | 5.94 | 6.22 | 4.73 | 4.13 | 5.06 | 6.54
3.66 | 6.21 | 4.78 | 4.24 | 5.79 | 5.61 | 5.68 | 7.21 | 6.86 | 5.76
5.53 | 6.72 | 4.4 | 6.93 | 6.67 | 6.18 | 8.02 | 5.99 | 7.06 | 7.77
8.02 | 6.48 | 5.52 | 5.25 | 6.99 | 5.23 | 6.22 | 5.21 | 4.33 | 5.54
4.44 | 5.34 | 8.61 | 7.63 | 5.07 | 8.13 | 6.33 | 7.86 | 4.38 | 5.99
7.2 | 6.14 | 6.92 | 7.06 | 6.25 | 6.91 | 5.03 | 4.97 | 6.44 | 4.27
6.58 | 6.57 | 4.68 | 7.91 | 5.32 | 4.57 | 6.43 | 5.65 | 5.23 | 5.06
5.64 | 3.69 | 6.07 | 4.76 | 3.49 | 7.4 | 7.05 | 8.84 | 7.43 | 7.26
5.26 | 5.81 | 7.55 | 5.84 | 6.17 | 4.63 | 6.36 | 7.64 | 7.09 | 6.94
7.51 | 4.82 | 4.8 | 6.11 | 7.11 | 6.84 | 5.09 | 5.69 | 6.68 | 6.25
6.67 | 5.61 | 6.03 | 4.96 | 7.51 | 6.6 | 6.65 | 6.08 | 4.35 | 7.19
5.02 | 4.7 | 5.25 | 3.68 | 4.38 | 5.69 | 5.33 | 5.14 | 6.07 | 5.51
8.31 | 6.89 | 8.1 | 5.83 | 6.12 | 8.11 | 4.2 | 7.75 | 6.84 | 7.21
5.08 | 6.99 | 4.71 | 5.31 | 5.5 | 4.8 | 4.79 | 3.28 | 6.5 | 5.32
7.64 | 6.26 | 7.75 | 3.82 | 6.58 | 7.3 | 6.04 | 5.62 | 8.91 | 5.93
5.23 | 5.87 | 4.57 | 6.02 | 6.16 | 4.91 | 6.28 | 6.16 | 5.61 | 6.18
5.67 | 6.28 | 6.35 | 5.8 | 3.94 | 5.75 | 5.92 | 5.52 | 3.59 | 6.83
6.03 | 6.32 | 4.9 | 6.62 | 7.12 | 7.22 | 6.22 | 3.59 | 5.24 | 4.55
6.24 | 3.94 | 7.32 | 3.88 | 5.7 | 7.94 | 6.1 | 5.31 | 6.84 | 5.85
4.76 | 7.24 | 5.52 | 5.58 | 3.64 | 3.87 | 6.74 | 5.74 | 5.62 | 6.08
6 | 5.91 | 6.65 | 4.92 | 3.84 | 8.12 | 4.6 | 6.15 | 5.18 | 7.81
6.55 | 4.47 | 4.09 | 7.05 | 6.1 | 7.91 | 6.26 | 7.5 | 3.39 | 5.8
4.75 | 8.34 | 4.15 | 4.44 | 7.57 | 7.5 | 4.12 | 6.19 | 3.54 | 6.07
4.66 | 6.58 | 6.15 | 6.57 | 5.2 | 8.53 | 6.63 | 5.82 | 7.85 | 6.69
4.05 | 5.76 | 6.37 | 6.23 | 6.97 | 6.84 | 7.21 | 7.69 | 4.92 | 4.8
5.4 | 5.51 | 4.79 | 5.27 | 8.38 | 5.71 | 6.4 | 5.43 | 5.45 | 8.09
6.85 | 7.5 | 6.74 | 6.46 | 6.44 | 5.68 | 5.78 | 4.79 | 6.21 | 7.68
6.28 | 7.05 | 5.39 | 5.42 | 5.82 | 5.29 | 6.21 | 6.97 | 4.6 | 5.97
7.9 | 4.51 | 6.24 | 6.71 | 7.66 | 5.53 | 7.15 | 4.81 | 3.93 | 5.33
5.39 | 5.71 | 3.92 | 5.35 | 6.47 | 4.2 | 3.94 | 5.59 | 5.49 | 4.66
4.99 | 4.14 | 5.97 | 6.72 | 3.82 | 6.42 | 4.44 | 5.04 | 5.41 | 4.46
6.17 | 5.55 | 6.33 | 5.9 | 4.68 | 6.27 | 7.47 | 7.06 | 5.16 | 6.98
4.96 | 5.45 | 6.35 | 4.35 | 5.9 | 5.07 | 4.65 | 7.22 | 5.2 | 5.73
8.63 | 4.42 | 4.4 | 8.04 | 5.99 | 6.36 | 5.2 | 5.02 | 7.63 | 3.79
4.67 | 6.84 | 5.48 | 3.66 | 5.95 | 7.82 | 6.59 | 6.47 | 7.32 | 7.9
4.6 | 4.74 | 6.21 | 6.48 | 5.72 | 6.5 | 6.32 | 7.58 | 4.11 | 3.98
6.05 | 3.34 | 6.83 | 6.06 | 5.44 | 6.04 | 4.87 | 4.58 | 5.11 | 7.73
5.07 | 5.82 | 6.47 | 5.44 | 3.95 | 4.93 | 5.74 | 5.63 | 6.85 | 6.01
5.19 | 7.32 | 6.17 | 5.72 | 8.46 | 3.78 | 6.9 | 4.73 | 5.85 | 5.8
7.96 | 5.85 | 7.2 | 7.22 | 4.89 | 6.75 | 6.82 | 6.56 | 7.81 | 6
4.49 | 8.49 | 5.5 | 6.26 | 5.86 | 5.11 | 4.57 | 5.2 | 6.03 | 6.72
5.67 | 6.33 | 7.35 | 5.91 | 5.98 | 8.3 | 8.35 | 5.29 | 4.99 | 7.1
3.59 | 6.05 | 4.49 | 5.25 | 5.31 | 6.67 | 5.26 | 5.41 | 7.14 | 6.97
7.44 | 4.65 | 3.54 | 4.38 | 4.11 | 5.91 | 5.05 | 6.27 | 7.77 | 5.31
4.23 | 4.57 | 4.89 | 4.89 | 7.97 | 6.71 | 6.05 | 6.64 | 7.92 | 7.44
6.86 | 3.45 | 3.64 | 5.82 | 7.16 | 6.47 | 5.68 | 6.14 | 4.91 | 6.64
7.15 | 7.03 | 7.24 | 7.21 | 4.05 | 5.96 | 5.63 | 7.19 | 6.8 | 6.32
5.21 | 7.9 | 5.51 | 7.09 | 4.42 | 7.11 | 7.72 | 7.37 | 7.59 | 4.2
5.46 | 6.04 | 7.35 | 6.12 | 6.51 | 5.29 | 6.07 | 6.48 | 7.2 | 5.05
4.83 | 5.28 | 7.25 | 6.89 | 7.06 | 7.45 | 6.52 | 7.03 | 6.05 | 6.92
5.76 | 6.68 | 6.28 | 4.75 | 4.68 | 6.97 | 3.8 | 8.06 | 5.35 | 4.2
7.6 | 8.53 | 6.18 | 6.04 | 5.23 | 6.46 | 5.86 | 6.26 | 3.95 | 5.67
6.34 | 6.08 | 5.35 | 5.81 | 5.56 | 6.86 | 5.93 | 3.97 | 6.05 | 3.59
4.34 | 7.57 | 5.28 | 8.51 | 5.86 | 8.06 | 6.55 | 3.88 | 5.55 | 4.59
4.72 | 5.25 | 5.78 | 8.02 | 5.93 | 4.78 | 3.41 | 7.79 | 8.31 | 4.45
5.1 | 7.66 | 6.19 | 5.29 | 5.41 | 5.26 | 5.91 | 8.36 | 8.07 | 6.61
4.76 | 4.2 | 3.74 | 6.47 | 6.05 | 6.48 | 5.57 | 7.93 | 6.03 | 4.6
8.75 | 6.53 | 3.49 | 6.27 | 4.46 | 4.95 | 5.63 | 5.14 | 5.65 | 4.34
6.58 | 6.25 | 4.58 | 4.61 | 7.55 | 7.26 | 7.38 | 5.91 | 6.71 | 4.93
4.77 | 4.19 | 4.92 | 5.78 | 7.64 | 6.06 | 5.15 | 6.08 | 6.95 | 3.73
7.83 | 8.57 | 5.6 | 8.19 | 7.09 | 6.91 | 6.81 | 3.94 | 7.13 | 6.09
5.64 | 8.16 | 5.97 | 6.51 | 7.96 | 6.24 | 6.91 | 7.91 | 3.69 | 3.68
6.4 | 6.06 | 6.14 | 8.57 | 3.41 | 5.28 | 8.51 | 5.87 | 8.75 | 3.64
7.7 | 5.48 | 5.9 | 4.28 | 6.47 | 7.35 | 7.15 | 5.33 | 5.65 | 6.32
4.27 | 5.24 | 3.47 | 7.03 | 5.29 | 4.67 | 5.54 | 5.03 | 5.46 | 6.22
4.38 | 7.41 | 4.34 | 5.77 | 6.1 | 4.39 | 4.71 | 5.88 | 8.25 | 6.55
6.52 | 6.77 | 5.84 | 7.8 | 7.01 | 4.72 | 6.56 | 6.87 | 7.44 | 5.4
6.25 | 6.17 | 4.61 | 4.74 | 4.94 | 5.69 | 5.96 | 6.56 | 8.15 | 7.72
8.12 | 5.33 | 6.95 | 5.3 | 6.8 | 4.83 | 5.73 | 6.62 | 5.58 | 6.48
6.88 | 6.62 | 7.64 | 3.94 | 8.51 | 6.96 | 4.87 | 5.95 | 3.91 | 6.86
6.15 | 7.38 | 6.38 | 6.97 | 4.98 | 6.77 | 4.45 | 6.86 | 6.04 | 5.21
7.19 | 6.5 | 4.11 | 4.43 | 6.23 | 6.6 | 5.39 | 6.36 | 6.27 | 7.37
5.85 | 8.06 | 5.06 | 5.11 | 7.42 | 5.85 | 6.67 | 4.08 | 5.87 | 5.56
3.47 | 5.42 | 4.14 | 7.72 | 5.69 | 4.36 | 6.09 | 6.03 | 5.32 | 4.78
7.25 | 7.74 | 6.48 | 4.65 | 5.77 | 6.18 | 4.41 | 8.25 | 3.83 | 7.58
6.22 | 4.68 | 6.98 | 5.76 | 6.38 | 6.49 | 3.53 | 7.88 | 6.91 | 5.75
4.81 | 7.47 | 7.7 | 8.16 | 4.1 | 4.66 | 4.25 | 5.66 | 5.09 | 6.05
5.38 | 5.06 | 5.59 | 8.24 | 4.53 | 6.5 | 7.64 | 5.77 | 8.11 | 7.03
5.45 | 4.17 | 6.57 | 3.45 | 4.79 | 5.99 | 8.72 | 7.37 | 6.46 | 8.38
7.03 | 4.86 | 5.58 | 4.95 | 8.19 | 6.41 | 6.37 | 3.95 | 6.62 | 5.51
5.17 | 6.46 | 6.13 | 4.8 | 5.2 | 6.56 | 6.44 | 4.54 | 6.54 | 5.45
5.29 | 6.71 | 5.8 | 6.05 | 5.64 | 7.67 | 8.25 | 7.66 | 5.7 | 6.35
4.45 | 7.12 | 8.47 | 6.59 | 6.93 | 6.85 | 4.23 | 7.31 | 6.06 | 6.26
6.27 | 5.46 | 5.62 | 7.75 | 5.04 | 4.93 | 5.8 | 5.69 | 4.36 | 5.79
6.16 | 6.65 | 7.08 | 6.96 | 3.66 | 5.16 | 4.75 | 4.11 | 4.88 | 8.01
4.82 | 6.83 | 4.97 | 6.93 | 5.33 | 5.8 | 5.15 | 6.72 | 5.95 | 3.78
5.48 | 5.7 | 5.46 | 5.98 | 7.02 | 5.55 | 4.66 | 7.06 | 6.25 | 7.53
4.42 | 7.2 | 3.95 | 7.3 | 6.44 | 7.08 | 4.32 | 7.11 | 5.22 | 7.78
5.78 | 6.18 | 5.9 | 5.18 | 6.11 | 6.51 | 6.92 | 7.56 | 6.96 | 5.22
3.51 | 8.11 | 7.8 | 5.5 | 5.74 | 6.86 | 5.42 | 6.02 | 6.54 | 4.86
4.23 | 7.84 | 5.98 | 7.48 | 4.73 | 4.75 | 7.03 | 5.11 | 6.97 | 5.9
6 | 7.28 | 6.05 | 7.9 | 4.03 | 3.39 | 4.22 | 7.23 | 5.41 | 4.12
5.36 | 5.82 | 6.73 | 8.36 | 4.62 | 7.84 | 7.83 | 5.97 | 7.27 | 4.88
5.92 | 6.19 | 5.17 | 5.34 | 7.09 | 5.89 | 7.63 | 4.71 | 4.41 | 7.32
5.98 | 7.02 | 5.11 | 3.16 | 6.71 | 8.28 | 5.33 | 6.94 | 5.2 | 5.41
3.95 | 6.21 | 6.54 | 6.05 | 5.92 | 6.1 | 6.16 | 6.73 | 7.5 | 6.8
5.77 | 5.13 | 6.24 | 7.6 | 6.92 | 4.03 | 3.75 | 3.66 | 6.56 | 5.55
4.98 | 5.61 | 6.94 | 5.01 | 4.84 | 4.63 | 4.5 | 4.72 | 4.17 | 5.91
7.28 | 6.7 | 6.53 | 6.2 | 5.38 | 5.5 | 5.87 | 6.11 | 4.04 | 7.06
7.11 | 6.23 | 5.79 | 6.28 | 6.08 | 6.63 | 6.99 | 6.32 | 4.66 | 4.58
7.44 | 8.08 | 5.91 | 6.89 | 6.9 | 4.09 | 5.69 | 6.13 | 5.69 | 5.83
4.11 | 3.97 | 6.39 | 4.26 | 4.52 | 7.66 | 5.47 | 4.34 | 4.72 | 5.16
8.21 | 5.79 | 6.49 | 4.93 | 6.83 | 4.09 | 5.33 | 6.57 | 7.51 | 4.93
5.56 | 5.45 | 7.21 | 4.94 | 3.92 | 4.53 | 5.98 | 6.89 | 4.34 | 5.97
7.64 | 6.16 | 7.54 | 7.26 | 7.43 | 7.88 | 8.41 | 6.07 | 6.25 | 4.36
7.24 | 6.13 | 6 | 7.56 | 5.14 | 5.27 | 6.66 | 6.73 | 6.28 | 6.22
5.52 | 5.92 | 6.5 | 5.66 | 7.7 | 5.31 | 4.36 | 5.61 | 6.06 | 8.27
7.42 | 7.01 | 5.97 | 4.11 | 6.2 | 4.44 | 8.63 | 7.74 | 7.14 | 5.37
7.76 | 5.95 | 6.81 | 7.49 | 5.74 | 7.2 | 5.75 | 6.33 | 7.03 | 6.76
7.27 | 3.9 | 6.14 | 5.51 | 5.44 | 6.16 | 5.91 | 6.59 | 6.73 | 6.23
4.85 | 7.07 | 7.5 | 4.81 | 4.14 | 5.28 | 5.07 | 4.78 | 4.58 | 6.36
6.02 | 4.54 | 7.47 | 6.11 | 6.03 | 7.95 | 5.48 | 4.55 | 4.24 | 3.7
6.26 | 5.22 | 3.84 | 6.44 | 6.78 | 5.9 | 4.83 | 7.26 | 6.17 | 5.39
5.89 | 5.85 | 6.05 | 6.05 | 7.8 | 5.34 | 5.11 | 5.34 | 4.51 | 6.92
6.66 | 5.78 | 6.89 | 5.66 | 7.11 | 6.9 | 4.13 | 4.61 | 4.49 | 4.84
5.08 | 7.8 | 5.41 | 6.07 | 5.84 | 6.06 | 6.14 | 5.48 | 8.3 | 6.44
6.52 | 5.86 | 4.45 | 5.49 | 6.13 | 6.83 | 5.75 | 8.66 | 7.38 | 5.45
4.4 | 6.48 | 5.92 | 6.74 | 6.89 | 4.74 | 3.85 | 3.73 | 8 | 6.12
8.18 | 4.28 | 4.47 | 6.12 | 3.8 | 5.53 | 6.1 | 6.25 | 6.22 | 4.75
3.9 | 3.79 | 6.8 | 8.79 | 8.44 | 3.56 | 4.63 | 8.1 | 4.72 | 4.69
5.22 | 5.48 | 5.33 | 6.11 | 6.07 | 4.79 | 5.04 | 5.51 | 6.11 | 6.14
7.77 | 4.69 | 6.67 | 8.1 | 6.02 | 6.93 | 7.62 | 8.3 | 8.36 | 5.36
4.24 | 4.66 | 5.03 | 5.73 | 7 | 6.36 | 6.62 | 5.81 | 4.4 | 7.17
7.78 | 6.24 | 5.17 | 5.59 | 6.83 | 4.64 | 5.94 | 5.85 | 4.16 | 4.95
8.57 | 6.92 | 8.49 | 3.47 | 4.06 | 5.93 | 4.61 | 5.9 | 5.36 | 7.59
7.41 | 8.66 | 5.59 | 3.25 | 6.41 | 8.84 | 3.72 | 4.31 | 7.9 | 7.75
5.23 | 5.26 | 6.58 | 6.54 | 6.84 | 4.96 | 6.97 | 7.25 | 5.13 | 6.64
6.02 | 7.16 | 5.37 | 5.85 | 5.45 | 5.64 | 6.12 | 3.49 | 5.33 | 5.96
7.09 | 3.83 | 6.06 | 8.41 | 7.59 | 6.56 | 5.27 | 5.17 | 6.05 | 6.36
6.73 | 6.97 | 6.58 | 6.85 | 5.08 | 7.03 | 6.65 | 6.95 | 5.27 | 6.18
3.53 | 5.83 | 5.93 | 6.1 | 7.47 | 5.13 | 6.09 | 6.33 | 6.18 | 6
3.39 | 7.09 | 5.62 | 5.46 | 5.25 | 6.01 | 6.14 | 7.18 | 5.93 | 4.42
6.84 | 6.01 | 5.44 | 8.26 | 5.64 | 7.42 | 3.66 | 7.83 | 6.53 | 8.57
7.37 | 5.95 | 6.75 | 3.79 | 5.6 | 5.24 | 6.06 | 6.99 | 7.02 | 7.09
6.11 | 6.81 | 4.86 | 5.91 | 4.82 | 4.41 | 3.45 | 5.39 | 5.33 | 5.49
5.95 | 6.1 | 5.88 | 5.36 | 5.59 | 6.35 | 6.95 | 6.61 | 8.57 | 8.19
7.19 | 5.66 | 6.55 | 4.38 | 7.8 | 4.58 | 5.99 | 6.83 | 6.15 | 6.44
5.24 | 5.9 | 6.48 | 5.16 | 4.45 | 7.79 | 7.06 | 6.91 | 7.46 | 7.01
7.32 | 4.27 | 4.73 | 6.38 | 6.06 | 5.82 | 3.54 | 6.43 | 6 | 7.33
6.46 | 4.29 | 5.91 | 6.38 | 6.28 | 5.49 | 5.53 | 5.88 | 6.1 | 6.94
6.5 | 8.36 | 6.67 | 6.9 | 8.34 | 8.49 | 5.18 | 5.5 | 5.01 | 6.04
5.68 | 4.22 | 4.97 | 4.73 | 6.07 | 5.92 | 4.85 | 6.6 | 5.59 | 5.93
4.8 | 7.23 | 6.59 | 5.79 | 7.87 | 4.42 | 5.44 | 7.32 | 7.05 | 5.15
5.13 | 5.27 | 5.78 | 5.92 | 8.32 | 6.27 | 6.71 | 5.31 | 8.18 | 6.26
5.49 | 6.23 | 4.96 | 5.83 | 6.53 | 4.98 | 4.92 | 3.7 | 8.01 | 6.73
5.35 | 5.47 | 5.73 | 6.53 | 5.85 | 5.63 | 5.58 | 5.34 | 5.54 | 6.16
7.87 | 8.55 | 7.24 | 5.65 | 4.59 | 6.25 | 6.76 | 6.24 | 4.2 | 5.74
7.08 | 4.02 | 6.43 | 5.41 | 7.9 | 6.42 | 6.49 | 4.32 | 6.12 | 8.59
7.49 | 4.09 | 6.71 | 3.49 | 5.8 | 7.89 | 4.27 | 5.58 | 5.11 | 5.62
8.01 | 7.55 | 5.08 | 4.31 | 4.79 | 4.54 | 4.82 | 4.16 | 5.46 | 5.61
5.16 | 4.52 | 6.48 | 7.3 | 5 | 6.79 | 5.62 | 5 | 5.04 | 5.99
7.04 | 6.42 | 7.41 | 5.52 | 6.18 | 5.75 | 6.37 | 7.14 | 8.61 | 7.98
5.76 | 5.18 | 4.89 | 4.39 | 6.46 | 4.72 | 6.15 | 3.45 | 3.43 | 6.15
6.41 | 7.79 | 7.37 | 6.17 | 5.33 | 7.74 | 8.53 | 5.72 | 6.19 | 5.09
5.48 | 4.6 | 8.21 | 5.31 | 4.6 | 6.28 | 5.71 | 5.43 | 4.17 | 3.8
6.14 | 5.43 | 7.14 | 6 | 6.48 | 7.66 | 7.29 | 5.01 | 5.55 | 8.21
7.75 | 5.99 | 6.01 | 7.19 | 5.11 | 4.23 | 7.17 | 3.61 | 3.56 | 5.2
6.2 | 5.23 | 7.2 | 7.7 | 6.37 | 5.29 | 7.52 | 4.85 | 8.32 | 5.36
4.56 | 6.91 | 6.5 | 7.7 | 4.03 | 7.7 | 4.68 | 6.25 | 8.66 | 6
4.36 | 3.74 | 4.74 | 5.93 | 6.08 | 3.85 | 8.61 | 7.21 | 5.6 | 5.86
6.16 | 6.51 | 7.38 | 6.79 | 5.49 | 4.16 | 4.75 | 5.64 | 7.09 | 8.75
4.09 | 4.32 | 6.77 | 4.58 | 7.26 | 3.28 | 6.19 | 4.49 | 4.38 | 7.52
7.23 | 8.35 | 5.24 | 5.85 | 4.65 | 8.42 | 4.17 | 4.98 | 7.72 | 5.81
4.73 | 6.18 | 7.33 | 5.86 | 5.67 | 7.09 | 5.11 | 7.73 | 6.42 | 6.5
4.78 | 5.02 | 6.92 | 7.23 | 5.46 | 6.77 | 6.42 | 7.27 | 6.16 | 6.04
7.71 | 4.56 | 7.46 | 5.38 | 5.05 | 4.65 | 3.62 | 5.93 | 4.42 | 4.94
5.79 | 7.25 | 7.48 | 6.54 | 6 | 8.03 | 3.81 | 6.92 | 7.08 | 5.21
5.94 | 6.03 | 7.17 | 7.38 | 6.84 | 7.49 | 4.34 | 5.91 | 5.05 | 4.68
4.92 | 4.44 | 5.28 | 5.17 | 4.88 | 4.12 | 4.17 | 5.01 | 4.69 | 7.3
4.64 | 3.93 | 8.02 | 6.27 | 7.87 | 4.19 | 7 | 5.9 | 6.24 | 6.58
5.14 | 7.93 | 3.86 | 3.96 | 8.47 | 6.28 | 6.03 | 6.44 | 5.48 | 8.41
6.96 | 6.69 | 7.16 | 4.7 | 5.97 | 4.23 | 6 | 4.84 | 6.01 | 8.16
4.6 | 6.03 | 7.67 | 7.58 | 6.05 | 5.24 | 7.96 | 7.47 | 8.2 | 6.71
5.09 | 3.81 | 4.19 | 8.05 | 8.42 | 3.53 | 5.19 | 6.41 | 8.02 | 4.5
4.58 | 5.75 | 4.25 | 6.97 | 6.28 | 6.81 | 6.5 | 6.23 | 6.79 | 5.77
4.78 | 8.59 | 4.56 | 4.51 | 4.91 | 6.05 | 3.87 | 5.59 | 7.12 | 7.91
7.66 | 4.88 | 7.58 | 3.75 | 7.93 | 8.46 | 5.84 | 6.05 | 6.34 | 5.96
6.18 | 3.7 | 6.59 | 8.44 | 7.13 | 5.47 | 6.2 | 5.96 | 4.39 | 5.23
5.74 | 3.87 | 4.16 | 5.3 | 7.6 | 6.92 | 7.74 | 5.01 | 4.47 | 3.75
7.63 | 6.56 | 3.56 | 5.95 | 7.58 | 5.56 | 3.59 | 4.26 | 6.78 | 5.23
5.59 | 8.2 | 6.61 | 5 | 5.08 | 7.58 | 4.56 | 6.98 | 3.99 | 5.85
6.48 | 4.34 | 6.16 | 5.48 | 6.28 | 4.76 | 4.72 | 5.19 | 5.77 | 5.72
5.85 | 8.31 | 7.08 | 5.88 | 5.92 | 5.74 | 7.13 | 5.27 | 6.1 | 6.1
4.68 | 7.26 | 3.09 | 5.61 | 6.38 | 3.45 | 5.58 | 5.81 | 4.96 | 5.22
8.53 | 6.59 | 7.97 | 4.76 | 3.88 | 8.57 | 5.13 | 4.33 | 5.83 | 6.64
3.84 | 6.27 | 6.22 | 6.56 | 3.98 | 5.39 | 6.03 | 7.04 | 3.31 | 7.23
5.86 | 7.18 | 3.68 | 6.14 | 4.27 | 7.43 | 8.66 | 4.89 | 6.2 | 7.24
4.39 | 5.92 | 5.24 | 6.63 | 5.12 | 3.59 | 7.4 | 7.97 | 6.21 | 5.86
5.01 | 6.99 | 7.23 | 3.51 | 5.49 | 5.73 | 7.71 | 4.09 | 7.01 | 6.96
8.25 | 3.49 | 6.33 | 5.88 | 5.54 | 6.09 | 6.24 | 6.76 | 8.41 | 5.68
6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91 | 8.91
0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582 | 0.582
3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09 | 3.09
3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672 | 3.672
4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254 | 4.254
4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836 | 4.836
5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418 | 5.418
6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582 | 6.582
7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164 | 7.164
7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746 | 7.746
8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328 | 8.328
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062 | 0.062
0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099
0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138 | 0.138
0.175 | 0.174 | 0.174 | 0.174 | 0.174 | 0.174 | 0.174 | 0.174 | 0.174 | 0.174
0.178 | 0.179 | 0.179 | 0.179 | 0.179 | 0.179 | 0.179 | 0.179 | 0.179 | 0.179
0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137 | 0.137
0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099 | 0.099
0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063 | 0.063
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087 | 0.087
0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186 | 0.186
0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324 | 0.324
0.499 | 0.498 | 0.498 | 0.498 | 0.498 | 0.498 | 0.498 | 0.498 | 0.498 | 0.498
0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677 | 0.677
0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814 | 0.814
0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913 | 0.913
0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976 | 0.976
1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001 | 1.001

## PMTable
1001 | Generated with the SIPmath™ Modeling Tools from ProbabilityManagement.org
| Index | Released
| Values | 6
| 1 |  | To download the free SIPmath Tools visit |  | https://www.probabilitymanagement.org/tools-1
2
| 3 |  | For articles in Analytics Magazine visit |  | http://viewer.zmags.com/publication/90ffcc6b#/90ffcc6b/29
| 4 |  |  | and | http://analytics-magazine.org/monte-carlo-for-the-masses/
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
9
0.3
6
6.3
6.6
6.9
7.2
7.5
7.8
8.1
8.4
8.7
9
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
0.01
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!